## 26035
Task_no | Task_name | task_owner | finish_date | project_complete_date | actual_finish_date | flag_func
1 | TRC COST DIW | Customer Services | 2026-03-08 | 2026-03-08
3 | Input Check COST DIW | Module Change | 2026-03-13 | 2026-03-13
4 | Induction Induction COST DIW | Planning and Business Support | 2026-03-15 | 2026-03-15 | 2026-03-15 | Induction
5 | Engine Bulk Strip COST DIW | Module Change | 2026-03-22 | 2026-03-22
6GATE 1 | Components Sentencing COST DIW | Module Change | 2026-03-26 | 2026-03-26
7 | Components Receipt at Vendor COST DIW | Logistics | 2026-04-02 | 2026-04-02
8GATE 1 | Engine Inspection COST DIW | Module Change | 2026-03-28 | 2026-03-28
9 | Module Strip COST DIW | Module Repair | 2026-03-28 | 2026-03-28
9-MODULE 31 | MODULE 31 Module Strip | Module Repair | 2026-03-28 | 2026-03-28
9-MODULE 32 | MODULE 32 Module Strip | Module Repair | 2026-03-28 | 2026-03-28
9-MODULE 33 | MODULE 33 Module Strip | Module Repair | 2026-03-28 | 2026-03-28
9-MODULE 41 | MODULE 41 Module Strip | Module Repair | 2026-03-28 | 2026-03-28
9-MODULE 51 | MODULE 51 Module Strip | Module Repair | 2026-03-28 | 2026-03-28
9-MODULE 52 | MODULE 52 Module Strip | Module Repair | 2026-03-28 | 2026-03-28
10GATE 1 | Critical Inspection | Module Repair | 2026-03-27 | 2026-03-27
13 | Critical Parts Orders | Material Management | 2026-03-28 | 2026-03-28
14 | Overseas Receipt At Vendor | Logistics | 2026-04-03 | 2026-04-03
15GATE 1 | Inspection BLT COST DIW | Bench | 2026-03-27 | 2026-03-27 |  | BLT
15-MODULE 31 | MODULE 31 Inspection | Bench | 2026-03-27 | 2026-03-27
15-MODULE 32 | MODULE 32 Inspection | Bench | 2026-03-27 | 2026-03-27
15-MODULE 33 | MODULE 33 Inspection | Bench | 2026-03-27 | 2026-03-27
15-MODULE 41 | MODULE 41 Inspection | Bench | 2026-03-27 | 2026-03-27
15-MODULE 51 | MODULE 51 Inspection | Bench | 2026-03-27 | 2026-03-27
15-MODULE 52 | MODULE 52 Inspection | Bench | 2026-03-27 | 2026-03-27
17 | Instruct external parts supply | Customer Services | 2026-03-23 | 2026-03-23
18 | Inspection (XWB HPC) | Bench | 2026-04-01 | 2026-04-01
19 | Parts orders | Material Management | 2026-04-02 | 2026-04-02
20 | Rework Spare Clock Stop | Material Management | 2026-04-06 | 2026-04-06
23 | Customer Material Approval | Customer Services | 2026-04-12 | 2026-04-12
27 | Kitting Review | Material Management | 2026-04-25 | 2026-04-25
28 | Component Repair BFS | Material Management | 2026-05-03 | 2026-05-03 |  | BFS
29 | Receive orders BFS | Material Management | 2026-05-03 | 2026-05-03 |  | BFS
30 | Receive overseas repair - core engine parts BFS | Material Management | 2026-04-29 | 2026-04-29 |  | BFS
31 | Core Module Parts Clock Stop | Material Management | 2026-05-01 | 2026-05-01
32GATE 2 | Core Modules Kitted BFS2 | Material Management | 2026-05-01 | 2026-04-27 |  | BFS2
32-MODULE 31 | MODULE 31 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27
32-MODULE 32 | MODULE 32 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27
32-MODULE 33 | MODULE 33 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27
32-MODULE 41 | MODULE 41 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27
32-MODULE 51 | MODULE 51 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27
32-MODULE 52 | MODULE 52 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27
33 | Module build BFS2 | Module Repair | 2026-05-07 | 2026-05-05 |  | BFS2
33-ENGINE MOUNT | ENGINE MOUNT Module build | Module Repair | 2026-05-05 | 2026-05-05
33-MODULE 31 | MODULE 31 Module build | Module Repair | 2026-05-05 | 2026-05-05
33-MODULE 32 | MODULE 32 Module build | Module Repair | 2026-05-05 | 2026-05-05
33-MODULE 33 | MODULE 33 Module build | Module Repair | 2026-05-05 | 2026-05-05
33-MODULE 41 | MODULE 41 Module build | Module Repair | 2026-05-05 | 2026-05-05
33-MODULE 51 | MODULE 51 Module build | Module Repair | 2026-05-05 | 2026-05-05
33-MODULE 52 | MODULE 52 Module build | Module Repair | 2026-05-05 | 2026-05-05
34 | Receive customer external parts | Customer Services | 2026-05-14 | 2026-05-14
35 | Receive external parts & components | Strategic Purchasing | 2026-05-14 | 2026-05-30 | 2026-04-16
36 | NMP Spare Clock Stop | Material Management | 2026-05-12 | 2026-05-12
37 | NMP Kitted BFS2 | Material Management | 2026-05-14 | 2026-05-14 |  | BFS2
38GATE 3 | Build Engine BFS2 | Module Change | 2026-05-23 | 2026-05-23 |  | BFS2
39 | Test MST | Module Change | 2026-05-25 | 2026-05-25 |  | MST
40GATE 4 | Ready For Despatch | Module Change | 2026-05-29 | 2026-05-29
41GATE 5 | Invoicing Pack | Planning and Business Support | 2026-03-15 | 2026-03-15

## 26035 (MST+26)
Task_no | Task_name | task_owner | finish_date | project_complete_date | actual_finish_date | flag_func | change_DF | change_PCD | change_ACD
1 | TRC COST DIW | Customer Services | 2026-03-08 | 2026-03-08 |  |  | 0 | 0 | 0
3 | Input Check COST DIW | Module Change | 2026-03-13 | 2026-03-13 |  |  | 0 | 0 | 0
4 | Induction Induction COST DIW | Planning and Business Support | 2026-03-15 | 2026-03-15 | 2026-03-15 | Induction | 0 | 0 | 0
5 | Engine Bulk Strip COST DIW | Module Change | 2026-03-22 | 2026-03-22 |  |  | 0 | 0 | 0
6GATE 1 | Components Sentencing COST DIW | Module Change | 2026-03-26 | 2026-03-26 |  |  | 0 | 0 | 0
7 | Components Receipt at Vendor COST DIW | Logistics | 2026-04-02 | 2026-04-02 |  |  | 0 | 0 | 0
8GATE 1 | Engine Inspection COST DIW | Module Change | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9 | Module Strip COST DIW | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 31 | MODULE 31 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 32 | MODULE 32 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 33 | MODULE 33 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 41 | MODULE 41 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 51 | MODULE 51 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 52 | MODULE 52 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
10GATE 1 | Critical Inspection | Module Repair | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
13 | Critical Parts Orders | Material Management | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
14 | Overseas Receipt At Vendor | Logistics | 2026-04-03 | 2026-04-03 |  |  | 0 | 0 | 0
15GATE 1 | Inspection BLT COST DIW | Bench | 2026-03-27 | 2026-03-27 |  | BLT | 0 | 0 | 0
15-MODULE 31 | MODULE 31 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 32 | MODULE 32 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 33 | MODULE 33 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 41 | MODULE 41 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 51 | MODULE 51 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 52 | MODULE 52 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
17 | Instruct external parts supply | Customer Services | 2026-03-23 | 2026-03-23 |  |  | 0 | 0 | 0
18 | Inspection (XWB HPC) | Bench | 2026-04-01 | 2026-04-01 |  |  | 0 | 0 | 0
19 | Parts orders | Material Management | 2026-04-02 | 2026-04-02 |  |  | 0 | 0 | 0
20 | Rework Spare Clock Stop | Material Management | 2026-04-06 | 2026-04-06 |  |  | 0 | 0 | 0
23 | Customer Material Approval | Customer Services | 2026-04-12 | 2026-04-12 |  |  | 0 | 0 | 0
27 | Kitting Review | Material Management | 2026-04-25 | 2026-04-25 |  |  | 0 | 0 | 0
28 | Component Repair BFS | Material Management | 2026-05-03 | 2026-05-03 |  | BFS | 0 | 0 | 0
29 | Receive orders BFS | Material Management | 2026-05-03 | 2026-05-03 |  | BFS | 0 | 0 | 0
30 | Receive overseas repair - core engine parts BFS | Material Management | 2026-04-29 | 2026-04-29 |  | BFS | 0 | 0 | 0
31 | Core Module Parts Clock Stop | Material Management | 2026-05-01 | 2026-05-01 |  |  | 0 | 0 | 0
32GATE 2 | Core Modules Kitted BFS2 | Material Management | 2026-05-01 | 2026-05-23 |  | BFS2 | 0 | 26 | 0
32-MODULE 31 | MODULE 31 Core Modules Kitted | Material Management | 2026-04-27 | 2026-05-23 |  |  | 0 | 26 | 0
32-MODULE 32 | MODULE 32 Core Modules Kitted | Material Management | 2026-04-27 | 2026-05-23 |  |  | 0 | 26 | 0
32-MODULE 33 | MODULE 33 Core Modules Kitted | Material Management | 2026-04-27 | 2026-05-23 |  |  | 0 | 26 | 0
32-MODULE 41 | MODULE 41 Core Modules Kitted | Material Management | 2026-04-27 | 2026-05-23 |  |  | 0 | 26 | 0
32-MODULE 51 | MODULE 51 Core Modules Kitted | Material Management | 2026-04-27 | 2026-05-23 |  |  | 0 | 26 | 0
32-MODULE 52 | MODULE 52 Core Modules Kitted | Material Management | 2026-04-27 | 2026-05-23 |  |  | 0 | 26 | 0
33 | Module build BFS2 | Module Repair | 2026-05-07 | 2026-05-31 |  | BFS2 | 0 | 26 | 0
33-ENGINE MOUNT | ENGINE MOUNT Module build | Module Repair | 2026-05-05 | 2026-05-31 |  |  | 0 | 26 | 0
33-MODULE 31 | MODULE 31 Module build | Module Repair | 2026-05-05 | 2026-05-31 |  |  | 0 | 26 | 0
33-MODULE 32 | MODULE 32 Module build | Module Repair | 2026-05-05 | 2026-05-31 |  |  | 0 | 26 | 0
33-MODULE 33 | MODULE 33 Module build | Module Repair | 2026-05-05 | 2026-05-31 |  |  | 0 | 26 | 0
33-MODULE 41 | MODULE 41 Module build | Module Repair | 2026-05-05 | 2026-05-31 |  |  | 0 | 26 | 0
33-MODULE 51 | MODULE 51 Module build | Module Repair | 2026-05-05 | 2026-05-31 |  |  | 0 | 26 | 0
33-MODULE 52 | MODULE 52 Module build | Module Repair | 2026-05-05 | 2026-05-31 |  |  | 0 | 26 | 0
34 | Receive customer external parts | Customer Services | 2026-05-14 | 2026-05-14 |  |  | 0 | 0 | 0
35 | Receive external parts & components | Strategic Purchasing | 2026-05-14 | 2026-05-30 | 2026-04-16 |  | 0 | 0 | 0
36 | NMP Spare Clock Stop | Material Management | 2026-05-12 | 2026-05-12 |  |  | 0 | 0 | 0
37 | NMP Kitted BFS2 | Material Management | 2026-05-14 | 2026-06-09 |  | BFS2 | 0 | 26 | 0
38GATE 3 | Build Engine BFS2 | Module Change | 2026-05-23 | 2026-06-18 |  | BFS2 | 0 | 26 | 0
39 | Test MST | Module Change | 2026-05-25 | 2026-06-20 |  | MST | 0 | 26 | 0
40GATE 4 | Ready For Despatch | Module Change | 2026-05-29 | 2026-05-29 |  |  | 0 | 0 | 0
41GATE 5 | Invoicing Pack | Planning and Business Support | 2026-03-15 | 2026-03-15 |  |  | 0 | 0 | 0

## 26035 (MST-26)
Task_no | Task_name | task_owner | finish_date | project_complete_date | actual_finish_date | flag_func | change_DF | change_PCD | change_ACD
1 | TRC COST DIW | Customer Services | 2026-03-08 | 2026-03-08 |  |  | 0 | 0 | 0
3 | Input Check COST DIW | Module Change | 2026-03-13 | 2026-03-13 |  |  | 0 | 0 | 0
4 | Induction Induction COST DIW | Planning and Business Support | 2026-03-15 | 2026-03-15 | 2026-03-15 | Induction | 0 | 0 | 0
5 | Engine Bulk Strip COST DIW | Module Change | 2026-03-22 | 2026-03-22 |  |  | 0 | 0 | 0
6GATE 1 | Components Sentencing COST DIW | Module Change | 2026-03-26 | 2026-03-26 |  |  | 0 | 0 | 0
7 | Components Receipt at Vendor COST DIW | Logistics | 2026-04-02 | 2026-04-02 |  |  | 0 | 0 | 0
8GATE 1 | Engine Inspection COST DIW | Module Change | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9 | Module Strip COST DIW | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 31 | MODULE 31 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 32 | MODULE 32 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 33 | MODULE 33 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 41 | MODULE 41 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 51 | MODULE 51 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 52 | MODULE 52 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
10GATE 1 | Critical Inspection | Module Repair | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
13 | Critical Parts Orders | Material Management | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
14 | Overseas Receipt At Vendor | Logistics | 2026-04-03 | 2026-04-03 |  |  | 0 | 0 | 0
15GATE 1 | Inspection BLT COST DIW | Bench | 2026-03-27 | 2026-03-27 |  | BLT | 0 | 0 | 0
15-MODULE 31 | MODULE 31 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 32 | MODULE 32 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 33 | MODULE 33 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 41 | MODULE 41 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 51 | MODULE 51 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 52 | MODULE 52 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
17 | Instruct external parts supply | Customer Services | 2026-03-23 | 2026-03-23 |  |  | 0 | 0 | 0
18 | Inspection (XWB HPC) | Bench | 2026-04-01 | 2026-04-01 |  |  | 0 | 0 | 0
19 | Parts orders | Material Management | 2026-04-02 | 2026-04-02 |  |  | 0 | 0 | 0
20 | Rework Spare Clock Stop | Material Management | 2026-04-06 | 2026-04-06 |  |  | 0 | 0 | 0
23 | Customer Material Approval | Customer Services | 2026-04-12 | 2026-04-12 |  |  | 0 | 0 | 0
27 | Kitting Review | Material Management | 2026-04-25 | 2026-04-25 |  |  | 0 | 0 | 0
28 | Component Repair BFS | Material Management | 2026-05-03 | 2026-05-03 |  | BFS | 0 | 0 | 0
29 | Receive orders BFS | Material Management | 2026-05-03 | 2026-05-03 |  | BFS | 0 | 0 | 0
30 | Receive overseas repair - core engine parts BFS | Material Management | 2026-04-29 | 2026-04-29 |  | BFS | 0 | 0 | 0
31 | Core Module Parts Clock Stop | Material Management | 2026-05-01 | 2026-05-01 |  |  | 0 | 0 | 0
32GATE 2 | Core Modules Kitted BFS2 | Material Management | 2026-05-01 | 2026-04-27 |  | BFS2 | 0 | 0 | 0
32-MODULE 31 | MODULE 31 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27 |  |  | 0 | 0 | 0
32-MODULE 32 | MODULE 32 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27 |  |  | 0 | 0 | 0
32-MODULE 33 | MODULE 33 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27 |  |  | 0 | 0 | 0
32-MODULE 41 | MODULE 41 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27 |  |  | 0 | 0 | 0
32-MODULE 51 | MODULE 51 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27 |  |  | 0 | 0 | 0
32-MODULE 52 | MODULE 52 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27 |  |  | 0 | 0 | 0
33 | Module build BFS2 | Module Repair | 2026-05-07 | 2026-05-05 |  | BFS2 | 0 | 0 | 0
33-ENGINE MOUNT | ENGINE MOUNT Module build | Module Repair | 2026-05-05 | 2026-05-05 |  |  | 0 | 0 | 0
33-MODULE 31 | MODULE 31 Module build | Module Repair | 2026-05-05 | 2026-05-05 |  |  | 0 | 0 | 0
33-MODULE 32 | MODULE 32 Module build | Module Repair | 2026-05-05 | 2026-05-05 |  |  | 0 | 0 | 0
33-MODULE 33 | MODULE 33 Module build | Module Repair | 2026-05-05 | 2026-05-05 |  |  | 0 | 0 | 0
33-MODULE 41 | MODULE 41 Module build | Module Repair | 2026-05-05 | 2026-05-05 |  |  | 0 | 0 | 0
33-MODULE 51 | MODULE 51 Module build | Module Repair | 2026-05-05 | 2026-05-05 |  |  | 0 | 0 | 0
33-MODULE 52 | MODULE 52 Module build | Module Repair | 2026-05-05 | 2026-05-05 |  |  | 0 | 0 | 0
34 | Receive customer external parts | Customer Services | 2026-05-14 | 2026-05-14 |  |  | 0 | 0 | 0
35 | Receive external parts & components | Strategic Purchasing | 2026-05-14 | 2026-05-30 | 2026-04-16 |  | 0 | 0 | 0
36 | NMP Spare Clock Stop | Material Management | 2026-05-12 | 2026-05-12 |  |  | 0 | 0 | 0
37 | NMP Kitted BFS2 | Material Management | 2026-05-14 | 2026-05-14 |  | BFS2 | 0 | 0 | 0
38GATE 3 | Build Engine BFS2 | Module Change | 2026-05-23 | 2026-05-23 |  | BFS2 | 0 | 0 | 0
39 | Test MST | Module Change | 2026-05-25 | 2026-05-25 |  | MST | 0 | 0 | 0
40GATE 4 | Ready For Despatch | Module Change | 2026-05-29 | 2026-05-29 |  |  | 0 | 0 | 0
41GATE 5 | Invoicing Pack | Planning and Business Support | 2026-03-15 | 2026-03-15 |  |  | 0 | 0 | 0

## 26035 (MST-5)
Task_no | Task_name | task_owner | finish_date | project_complete_date | actual_finish_date | flag_func | change_DF | change_PCD | change_ACD
1 | TRC COST DIW | Customer Services | 2026-03-08 | 2026-03-08 |  |  | 0 | 0 | 0
3 | Input Check COST DIW | Module Change | 2026-03-13 | 2026-03-13 |  |  | 0 | 0 | 0
4 | Induction Induction COST DIW | Planning and Business Support | 2026-03-15 | 2026-03-15 | 2026-03-15 | Induction | 0 | 0 | 0
5 | Engine Bulk Strip COST DIW | Module Change | 2026-03-22 | 2026-03-22 |  |  | 0 | 0 | 0
6GATE 1 | Components Sentencing COST DIW | Module Change | 2026-03-26 | 2026-03-26 |  |  | 0 | 0 | 0
7 | Components Receipt at Vendor COST DIW | Logistics | 2026-04-02 | 2026-04-02 |  |  | 0 | 0 | 0
8GATE 1 | Engine Inspection COST DIW | Module Change | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9 | Module Strip COST DIW | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 31 | MODULE 31 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 32 | MODULE 32 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 33 | MODULE 33 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 41 | MODULE 41 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 51 | MODULE 51 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 52 | MODULE 52 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
10GATE 1 | Critical Inspection | Module Repair | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
13 | Critical Parts Orders | Material Management | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
14 | Overseas Receipt At Vendor | Logistics | 2026-04-03 | 2026-04-03 |  |  | 0 | 0 | 0
15GATE 1 | Inspection BLT COST DIW | Bench | 2026-03-27 | 2026-03-27 |  | BLT | 0 | 0 | 0
15-MODULE 31 | MODULE 31 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 32 | MODULE 32 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 33 | MODULE 33 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 41 | MODULE 41 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 51 | MODULE 51 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 52 | MODULE 52 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
17 | Instruct external parts supply | Customer Services | 2026-03-23 | 2026-03-23 |  |  | 0 | 0 | 0
18 | Inspection (XWB HPC) | Bench | 2026-04-01 | 2026-04-01 |  |  | 0 | 0 | 0
19 | Parts orders | Material Management | 2026-04-02 | 2026-04-02 |  |  | 0 | 0 | 0
20 | Rework Spare Clock Stop | Material Management | 2026-04-06 | 2026-04-06 |  |  | 0 | 0 | 0
23 | Customer Material Approval | Customer Services | 2026-04-12 | 2026-04-12 |  |  | 0 | 0 | 0
27 | Kitting Review | Material Management | 2026-04-25 | 2026-04-25 |  |  | 0 | 0 | 0
28 | Component Repair BFS | Material Management | 2026-05-03 | 2026-05-03 | 2026-04-15 | BFS | 0 | 0 | 46127 | <- no change if ACD is filled
29 | Receive orders BFS | Material Management | 2026-05-03 | 2026-04-28 |  | BFS | 0 | -5 | 0 | <- date change even the task disabled
30 | Receive overseas repair - core engine parts BFS | Material Management | 2026-04-29 | 2026-04-24 |  | BFS | 0 | -5 | 0
31 | Core Module Parts Clock Stop | Material Management | 2026-05-01 | 2026-05-01 |  |  | 0 | 0 | 0
32GATE 2 | Core Modules Kitted BFS2 | Material Management | 2026-05-01 | 2026-04-22 |  | BFS2 | 0 | -5 | 0
32-MODULE 31 | MODULE 31 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-22 |  |  | 0 | -5 | 0
32-MODULE 32 | MODULE 32 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-22 |  |  | 0 | -5 | 0
32-MODULE 33 | MODULE 33 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-22 |  |  | 0 | -5 | 0
32-MODULE 41 | MODULE 41 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-22 |  |  | 0 | -5 | 0
32-MODULE 51 | MODULE 51 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-22 |  |  | 0 | -5 | 0
32-MODULE 52 | MODULE 52 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-22 |  |  | 0 | -5 | 0
33 | Module build BFS2 | Module Repair | 2026-05-07 | 2026-04-30 |  | BFS2 | 0 | -5 | 0
33-ENGINE MOUNT | ENGINE MOUNT Module build | Module Repair | 2026-05-05 | 2026-04-30 |  |  | 0 | -5 | 0 | <- date change even the task disabled
33-MODULE 31 | MODULE 31 Module build | Module Repair | 2026-05-05 | 2026-04-30 |  |  | 0 | -5 | 0
33-MODULE 32 | MODULE 32 Module build | Module Repair | 2026-05-05 | 2026-04-30 |  |  | 0 | -5 | 0
33-MODULE 33 | MODULE 33 Module build | Module Repair | 2026-05-05 | 2026-04-30 |  |  | 0 | -5 | 0
33-MODULE 41 | MODULE 41 Module build | Module Repair | 2026-05-05 | 2026-04-30 |  |  | 0 | -5 | 0
33-MODULE 51 | MODULE 51 Module build | Module Repair | 2026-05-05 | 2026-04-30 |  |  | 0 | -5 | 0
33-MODULE 52 | MODULE 52 Module build | Module Repair | 2026-05-05 | 2026-04-30 |  |  | 0 | -5 | 0
34 | Receive customer external parts | Customer Services | 2026-05-14 | 2026-05-14 |  |  | 0 | 0 | 0
35 | Receive external parts & components | Strategic Purchasing | 2026-05-14 | 2026-05-30 | 2026-04-16 |  | 0 | 0 | 0
36 | NMP Spare Clock Stop | Material Management | 2026-05-12 | 2026-05-12 |  |  | 0 | 0 | 0
37 | NMP Kitted BFS2 | Material Management | 2026-05-14 | 2026-05-09 |  | BFS2 | 0 | -5 | 0
38GATE 3 | Build Engine BFS2 | Module Change | 2026-05-23 | 2026-05-18 |  | BFS2 | 0 | -5 | 0
39 | Test MST | Module Change | 2026-05-25 | 2026-05-20 |  | MST | 0 | -5 | 0
40GATE 4 | Ready For Despatch | Module Change | 2026-05-29 | 2026-05-29 |  |  | 0 | 0 | 0
41GATE 5 | Invoicing Pack | Planning and Business Support | 2026-03-15 | 2026-03-15 |  |  | 0 | 0 | 0

## 26035 (MST+5)
Task_no | Task_name | task_owner | finish_date | project_complete_date | actual_finish_date | flag_func | change_DF | change_PCD | change_ACD
1 | TRC COST DIW | Customer Services | 2026-03-08 | 2026-03-08 |  |  | 0 | 0 | 0
3 | Input Check COST DIW | Module Change | 2026-03-13 | 2026-03-13 |  |  | 0 | 0 | 0
4 | Induction Induction COST DIW | Planning and Business Support | 2026-03-15 | 2026-03-15 | 2026-03-15 | Induction | 0 | 0 | 0
5 | Engine Bulk Strip COST DIW | Module Change | 2026-03-22 | 2026-03-22 |  |  | 0 | 0 | 0
6GATE 1 | Components Sentencing COST DIW | Module Change | 2026-03-26 | 2026-03-26 |  |  | 0 | 0 | 0
7 | Components Receipt at Vendor COST DIW | Logistics | 2026-04-02 | 2026-04-02 |  |  | 0 | 0 | 0
8GATE 1 | Engine Inspection COST DIW | Module Change | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9 | Module Strip COST DIW | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 31 | MODULE 31 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 32 | MODULE 32 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 33 | MODULE 33 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 41 | MODULE 41 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 51 | MODULE 51 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 52 | MODULE 52 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
10GATE 1 | Critical Inspection | Module Repair | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
13 | Critical Parts Orders | Material Management | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
14 | Overseas Receipt At Vendor | Logistics | 2026-04-03 | 2026-04-03 |  |  | 0 | 0 | 0
15GATE 1 | Inspection BLT COST DIW | Bench | 2026-03-27 | 2026-03-27 |  | BLT | 0 | 0 | 0
15-MODULE 31 | MODULE 31 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 32 | MODULE 32 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 33 | MODULE 33 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 41 | MODULE 41 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 51 | MODULE 51 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 52 | MODULE 52 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
17 | Instruct external parts supply | Customer Services | 2026-03-23 | 2026-03-23 |  |  | 0 | 0 | 0
18 | Inspection (XWB HPC) | Bench | 2026-04-01 | 2026-04-01 |  |  | 0 | 0 | 0
19 | Parts orders | Material Management | 2026-04-02 | 2026-04-02 |  |  | 0 | 0 | 0
20 | Rework Spare Clock Stop | Material Management | 2026-04-06 | 2026-04-06 |  |  | 0 | 0 | 0
23 | Customer Material Approval | Customer Services | 2026-04-12 | 2026-04-12 |  |  | 0 | 0 | 0
27 | Kitting Review | Material Management | 2026-04-25 | 2026-04-25 |  |  | 0 | 0 | 0
28 | Component Repair BFS | Material Management | 2026-05-03 | 2026-05-03 | 2026-04-15 | BFS | 0 | 0 | 46127
29 | Receive orders BFS | Material Management | 2026-05-03 | 2026-05-03 |  | BFS | 0 | 0 | 0
30 | Receive overseas repair - core engine parts BFS | Material Management | 2026-04-29 | 2026-04-29 |  | BFS | 0 | 0 | 0
31 | Core Module Parts Clock Stop | Material Management | 2026-05-01 | 2026-05-01 |  |  | 0 | 0 | 0
32GATE 2 | Core Modules Kitted BFS2 | Material Management | 2026-05-01 | 2026-04-27 |  | BFS2 | 0 | 0 | 0
32-MODULE 31 | MODULE 31 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27 |  |  | 0 | 0 | 0
32-MODULE 32 | MODULE 32 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27 |  |  | 0 | 0 | 0
32-MODULE 33 | MODULE 33 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27 |  |  | 0 | 0 | 0
32-MODULE 41 | MODULE 41 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27 |  |  | 0 | 0 | 0
32-MODULE 51 | MODULE 51 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27 |  |  | 0 | 0 | 0
32-MODULE 52 | MODULE 52 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27 |  |  | 0 | 0 | 0
33 | Module build BFS2 | Module Repair | 2026-05-07 | 2026-05-05 |  | BFS2 | 0 | 0 | 0
33-ENGINE MOUNT | ENGINE MOUNT Module build | Module Repair | 2026-05-05 | 2026-05-05 |  |  | 0 | 0 | 0
33-MODULE 31 | MODULE 31 Module build | Module Repair | 2026-05-05 | 2026-05-05 |  |  | 0 | 0 | 0
33-MODULE 32 | MODULE 32 Module build | Module Repair | 2026-05-05 | 2026-05-05 |  |  | 0 | 0 | 0
33-MODULE 33 | MODULE 33 Module build | Module Repair | 2026-05-05 | 2026-05-05 |  |  | 0 | 0 | 0
33-MODULE 41 | MODULE 41 Module build | Module Repair | 2026-05-05 | 2026-05-05 |  |  | 0 | 0 | 0
33-MODULE 51 | MODULE 51 Module build | Module Repair | 2026-05-05 | 2026-05-05 |  |  | 0 | 0 | 0
33-MODULE 52 | MODULE 52 Module build | Module Repair | 2026-05-05 | 2026-05-05 |  |  | 0 | 0 | 0
34 | Receive customer external parts | Customer Services | 2026-05-14 | 2026-05-14 |  |  | 0 | 0 | 0
35 | Receive external parts & components | Strategic Purchasing | 2026-05-14 | 2026-05-30 | 2026-04-16 |  | 0 | 0 | 0
36 | NMP Spare Clock Stop | Material Management | 2026-05-12 | 2026-05-12 |  |  | 0 | 0 | 0
37 | NMP Kitted BFS2 | Material Management | 2026-05-14 | 2026-05-14 |  | BFS2 | 0 | 0 | 0
38GATE 3 | Build Engine BFS2 | Module Change | 2026-05-23 | 2026-05-23 |  | BFS2 | 0 | 0 | 0
39 | Test MST | Module Change | 2026-05-25 | 2026-05-25 |  | MST | 0 | 0 | 0
40GATE 4 | Ready For Despatch | Module Change | 2026-05-29 | 2026-05-29 |  |  | 0 | 0 | 0
41GATE 5 | Invoicing Pack | Planning and Business Support | 2026-03-15 | 2026-03-15 |  |  | 0 | 0 | 0

## 26035 (MST hit BLT)
Task_no | Task_name | task_owner | finish_date | project_complete_date | actual_finish_date | flag_func | change_DF | change_PCD | change_ACD
1 | TRC COST DIW | Customer Services | 2026-03-08 | 2026-03-08 |  |  | 0 | 0 | 0
3 | Input Check COST DIW | Module Change | 2026-03-13 | 2026-03-13 |  |  | 0 | 0 | 0
4 | Induction Induction COST DIW | Planning and Business Support | 2026-03-15 | 2026-03-15 | 2026-03-15 | Induction | 0 | 0 | 0
5 | Engine Bulk Strip COST DIW | Module Change | 2026-03-22 | 2026-03-22 |  |  | 0 | 0 | 0
6GATE 1 | Components Sentencing COST DIW | Module Change | 2026-03-26 | 2026-03-26 |  |  | 0 | 0 | 0
7 | Components Receipt at Vendor COST DIW | Logistics | 2026-04-02 | 2026-04-02 |  |  | 0 | 0 | 0
8GATE 1 | Engine Inspection COST DIW | Module Change | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9 | Module Strip COST DIW | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 31 | MODULE 31 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 32 | MODULE 32 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 33 | MODULE 33 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 41 | MODULE 41 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 51 | MODULE 51 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 52 | MODULE 52 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
10GATE 1 | Critical Inspection | Module Repair | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
13 | Critical Parts Orders | Material Management | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
14 | Overseas Receipt At Vendor | Logistics | 2026-04-03 | 2026-04-03 |  |  | 0 | 0 | 0
15GATE 1 | Inspection BLT COST DIW | Bench | 2026-03-27 | 2026-03-27 |  | BLT | 0 | 0 | 0
15-MODULE 31 | MODULE 31 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 32 | MODULE 32 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 33 | MODULE 33 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 41 | MODULE 41 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 51 | MODULE 51 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 52 | MODULE 52 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
17 | Instruct external parts supply | Customer Services | 2026-03-23 | 2026-03-23 |  |  | 0 | 0 | 0
18 | Inspection (XWB HPC) | Bench | 2026-04-01 | 2026-04-01 |  |  | 0 | 0 | 0
19 | Parts orders | Material Management | 2026-04-02 | 2026-04-02 |  |  | 0 | 0 | 0
20 | Rework Spare Clock Stop | Material Management | 2026-04-06 | 2026-04-06 |  |  | 0 | 0 | 0
23 | Customer Material Approval | Customer Services | 2026-04-12 | 2026-04-12 |  |  | 0 | 0 | 0
27 | Kitting Review | Material Management | 2026-04-25 | 2026-04-25 |  |  | 0 | 0 | 0
28 | Component Repair BFS | Material Management | 2026-05-03 | 2026-05-03 | 2026-04-15 | BFS | 0 | 0 | 46127
29 | Receive orders BFS | Material Management | 2026-05-03 | 2026-03-27 |  | BFS | 0 | -37 | 0
30 | Receive overseas repair - core engine parts BFS | Material Management | 2026-04-29 | 2026-03-27 |  | BFS | 0 | -33 | 0
31 | Core Module Parts Clock Stop | Material Management | 2026-05-01 | 2026-05-01 |  |  | 0 | 0 | 0
32GATE 2 | Core Modules Kitted BFS2 | Material Management | 2026-05-01 | 2026-03-27 |  | BFS2 | 0 | -31 | 0
32-MODULE 31 | MODULE 31 Core Modules Kitted | Material Management | 2026-04-27 | 2026-03-27 |  |  | 0 | -31 | 0
32-MODULE 32 | MODULE 32 Core Modules Kitted | Material Management | 2026-04-27 | 2026-03-27 |  |  | 0 | -31 | 0
32-MODULE 33 | MODULE 33 Core Modules Kitted | Material Management | 2026-04-27 | 2026-03-27 |  |  | 0 | -31 | 0
32-MODULE 41 | MODULE 41 Core Modules Kitted | Material Management | 2026-04-27 | 2026-03-27 |  |  | 0 | -31 | 0
32-MODULE 51 | MODULE 51 Core Modules Kitted | Material Management | 2026-04-27 | 2026-03-27 |  |  | 0 | -31 | 0
32-MODULE 52 | MODULE 52 Core Modules Kitted | Material Management | 2026-04-27 | 2026-03-27 |  |  | 0 | -31 | 0
33 | Module build BFS2 | Module Repair | 2026-05-07 | 2026-03-27 |  | BFS2 | 0 | -39 | 0
33-ENGINE MOUNT | ENGINE MOUNT Module build | Module Repair | 2026-05-05 | 2026-03-27 |  |  | 0 | -39 | 0
33-MODULE 31 | MODULE 31 Module build | Module Repair | 2026-05-05 | 2026-03-27 |  |  | 0 | -39 | 0
33-MODULE 32 | MODULE 32 Module build | Module Repair | 2026-05-05 | 2026-03-27 |  |  | 0 | -39 | 0
33-MODULE 33 | MODULE 33 Module build | Module Repair | 2026-05-05 | 2026-03-27 |  |  | 0 | -39 | 0
33-MODULE 41 | MODULE 41 Module build | Module Repair | 2026-05-05 | 2026-03-27 |  |  | 0 | -39 | 0
33-MODULE 51 | MODULE 51 Module build | Module Repair | 2026-05-05 | 2026-03-27 |  |  | 0 | -39 | 0
33-MODULE 52 | MODULE 52 Module build | Module Repair | 2026-05-05 | 2026-03-27 |  |  | 0 | -39 | 0
34 | Receive customer external parts | Customer Services | 2026-05-14 | 2026-05-14 |  |  | 0 | 0 | 0
35 | Receive external parts & components | Strategic Purchasing | 2026-05-14 | 2026-05-30 | 2026-04-16 |  | 0 | 0 | 0
36 | NMP Spare Clock Stop | Material Management | 2026-05-12 | 2026-05-12 |  |  | 0 | 0 | 0
37 | NMP Kitted BFS2 | Material Management | 2026-05-14 | 2026-03-27 |  | BFS2 | 0 | -48 | 0
38GATE 3 | Build Engine BFS2 | Module Change | 2026-05-23 | 2026-03-27 |  | BFS2 | 0 | -57 | 0
39 | Test MST | Module Change | 2026-05-25 | 2026-03-27 |  | MST | 0 | -59 | 0
40GATE 4 | Ready For Despatch | Module Change | 2026-05-29 | 2026-05-29 |  |  | 0 | 0 | 0
41GATE 5 | Invoicing Pack | Planning and Business Support | 2026-03-15 | 2026-03-15 |  |  | 0 | 0 | 0

## 26035 (MST back to original)
Task_no | Task_name | task_owner | finish_date | project_complete_date | actual_finish_date | flag_func | change_DF | change_PCD | change_ACD
1 | TRC COST DIW | Customer Services | 2026-03-08 | 2026-03-08 |  |  | 0 | 0 | 0
3 | Input Check COST DIW | Module Change | 2026-03-13 | 2026-03-13 |  |  | 0 | 0 | 0
4 | Induction Induction COST DIW | Planning and Business Support | 2026-03-15 | 2026-03-15 | 2026-03-15 | Induction | 0 | 0 | 0
5 | Engine Bulk Strip COST DIW | Module Change | 2026-03-22 | 2026-03-22 |  |  | 0 | 0 | 0
6GATE 1 | Components Sentencing COST DIW | Module Change | 2026-03-26 | 2026-03-26 |  |  | 0 | 0 | 0
7 | Components Receipt at Vendor COST DIW | Logistics | 2026-04-02 | 2026-04-02 |  |  | 0 | 0 | 0
8GATE 1 | Engine Inspection COST DIW | Module Change | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9 | Module Strip COST DIW | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 31 | MODULE 31 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 32 | MODULE 32 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 33 | MODULE 33 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 41 | MODULE 41 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 51 | MODULE 51 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
9-MODULE 52 | MODULE 52 Module Strip | Module Repair | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
10GATE 1 | Critical Inspection | Module Repair | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
13 | Critical Parts Orders | Material Management | 2026-03-28 | 2026-03-28 |  |  | 0 | 0 | 0
14 | Overseas Receipt At Vendor | Logistics | 2026-04-03 | 2026-04-03 |  |  | 0 | 0 | 0
15GATE 1 | Inspection BLT COST DIW | Bench | 2026-03-27 | 2026-03-27 |  | BLT | 0 | 0 | 0
15-MODULE 31 | MODULE 31 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 32 | MODULE 32 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 33 | MODULE 33 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 41 | MODULE 41 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 51 | MODULE 51 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
15-MODULE 52 | MODULE 52 Inspection | Bench | 2026-03-27 | 2026-03-27 |  |  | 0 | 0 | 0
17 | Instruct external parts supply | Customer Services | 2026-03-23 | 2026-03-23 |  |  | 0 | 0 | 0
18 | Inspection (XWB HPC) | Bench | 2026-04-01 | 2026-04-01 |  |  | 0 | 0 | 0
19 | Parts orders | Material Management | 2026-04-02 | 2026-04-02 |  |  | 0 | 0 | 0
20 | Rework Spare Clock Stop | Material Management | 2026-04-06 | 2026-04-06 |  |  | 0 | 0 | 0
23 | Customer Material Approval | Customer Services | 2026-04-12 | 2026-04-12 |  |  | 0 | 0 | 0
27 | Kitting Review | Material Management | 2026-04-25 | 2026-04-25 |  |  | 0 | 0 | 0
28 | Component Repair BFS | Material Management | 2026-05-03 | 2026-05-03 | 2026-04-15 | BFS | 0 | 0 | 46127
29 | Receive orders BFS | Material Management | 2026-05-03 | 2026-05-03 |  | BFS | 0 | 0 | 0
30 | Receive overseas repair - core engine parts BFS | Material Management | 2026-04-29 | 2026-04-29 |  | BFS | 0 | 0 | 0
31 | Core Module Parts Clock Stop | Material Management | 2026-05-01 | 2026-05-01 |  |  | 0 | 0 | 0
32GATE 2 | Core Modules Kitted BFS2 | Material Management | 2026-05-01 | 2026-04-27 |  | BFS2 | 0 | 0 | 0
32-MODULE 31 | MODULE 31 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27 |  |  | 0 | 0 | 0
32-MODULE 32 | MODULE 32 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27 |  |  | 0 | 0 | 0
32-MODULE 33 | MODULE 33 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27 |  |  | 0 | 0 | 0
32-MODULE 41 | MODULE 41 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27 |  |  | 0 | 0 | 0
32-MODULE 51 | MODULE 51 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27 |  |  | 0 | 0 | 0
32-MODULE 52 | MODULE 52 Core Modules Kitted | Material Management | 2026-04-27 | 2026-04-27 |  |  | 0 | 0 | 0
33 | Module build BFS2 | Module Repair | 2026-05-07 | 2026-05-05 |  | BFS2 | 0 | 0 | 0
33-ENGINE MOUNT | ENGINE MOUNT Module build | Module Repair | 2026-05-05 | 2026-05-05 |  |  | 0 | 0 | 0
33-MODULE 31 | MODULE 31 Module build | Module Repair | 2026-05-05 | 2026-05-05 |  |  | 0 | 0 | 0
33-MODULE 32 | MODULE 32 Module build | Module Repair | 2026-05-05 | 2026-05-05 |  |  | 0 | 0 | 0
33-MODULE 33 | MODULE 33 Module build | Module Repair | 2026-05-05 | 2026-05-05 |  |  | 0 | 0 | 0
33-MODULE 41 | MODULE 41 Module build | Module Repair | 2026-05-05 | 2026-05-05 |  |  | 0 | 0 | 0
33-MODULE 51 | MODULE 51 Module build | Module Repair | 2026-05-05 | 2026-05-05 |  |  | 0 | 0 | 0
33-MODULE 52 | MODULE 52 Module build | Module Repair | 2026-05-05 | 2026-05-05 |  |  | 0 | 0 | 0
34 | Receive customer external parts | Customer Services | 2026-05-14 | 2026-05-14 |  |  | 0 | 0 | 0
35 | Receive external parts & components | Strategic Purchasing | 2026-05-14 | 2026-05-30 | 2026-04-16 |  | 0 | 0 | 0
36 | NMP Spare Clock Stop | Material Management | 2026-05-12 | 2026-05-12 |  |  | 0 | 0 | 0
37 | NMP Kitted BFS2 | Material Management | 2026-05-14 | 2026-05-14 |  | BFS2 | 0 | 0 | 0
38GATE 3 | Build Engine BFS2 | Module Change | 2026-05-23 | 2026-05-23 |  | BFS2 | 0 | 0 | 0
39 | Test MST | Module Change | 2026-05-25 | 2026-05-25 |  | MST | 0 | 0 | 0
40GATE 4 | Ready For Despatch | Module Change | 2026-05-29 | 2026-05-29 |  |  | 0 | 0 | 0
41GATE 5 | Invoicing Pack | Planning and Business Support | 2026-03-15 | 2026-03-15 |  |  | 0 | 0 | 0