## raw
Item No. | Section | Issue | MoSCoW | Issue Type (None/Bug/Rework/Enhancement) by HAESL | Comments | Issue Raise Date | Raised by | Screen Capture | Issue Type (None/Bug/Rework/Enhancement) by RR | Priority Classification (by RR) | User Story No (by RR) | Comments (by RR) | Change Request Accepted by HAESL(For Enhancements Only) | HAESL Comments | Comment date, Commented by | Closed/Fixed/Not yet fix
1 | Admin - Task Owner Setting | System | Must | Bug | Duplicate User show in the list when click "MR" | 2026-03-16 | Ray | Refer to Screen Capture | Bug | P4 |  | Suspecting this can be observed when two users performing same operation at atime. Not able to reproduce it in dev by single user |  | Low, no issue now |  | Fixed
2 | Admin - Template Management | UI | Must | Bug | Please remove "Hospital", "Check & Repair", "1st Refurbishment", "2nd Refurbishment", "Mature Refurbishment" from the dropdown list. | 2026-03-16 | Ray | Refer to Screen Capture | Bug | P4 |  | Entries to be removed |  | Low, no issue now |  | Fixed
Add "OH" in the list
3 | Admin - Gate Setting | System | Must | Bug | Unable to show gate "1A" after create. | 2026-03-16 | Ray | Refer to Screen Capture | Bug | P4 |  | Suspecting this can be observed when two users performing same operation at atime. Not able to reproduce it in dev by single user |  | Low, no issue now |  | Fixed
4 | Notification | System | Must | Bug | Unable to clear notifcations from notifcation list. After clicking the "X", the same notifcation will pop up again later, all the notifications become accumulate as a huge list. | 2026-03-16 | Ray | Refer to Screen Capture | None |  |  | Not able to reproduce in dev |  | Low, but the counter of msg delayed |  | Fixed
5 | Planner - Create Streamer | System | Must | Bug | Induction date cannot be backdated. | 2026-03-16 | Ricky | Refer to Screen Capture | Bug | P2 |  | Fixed |  | Medium, not fixed |  | Unstable Fix
6 | Planner - Create Streamer | System | Must | Bug | Dispatch Module S/N cannot be updated. | 2026-03-16 | Ricky | Refer to Screen Capture | None |  |  | As per requirement |  | Medium |  | Fixed
7 | Planner - Task | UI | Should | Bug | The table cells borders is not align | 2026-03-17 | Ray | Refer to Screen Capture | Bug | P4 |  | Working with Syncfusion on it |  | Low, not yet fixed |  | Not yet fix
8 | Planner - Task | System | Must | Bug | Showing unexpected date range after filter | 2026-03-17 | Ray | Refer to Screen Capture | None |  |  |  |  | High, function disappeared |  | Not yet fix
9 | Planner - Task | System | Must | Rework | Missing implement of Post UAT item U08 | 2026-03-17 | Ray | Refer to Screen Capture | None |  |  |  |  | Removed |  | Closed
10 | Planner - Create Streamer / Edit Streamer | System | Must | None | Inconsistency of value "Retain", if the row added by user, system shows "Retain", if the row is recongnise by PDF, system show "RETAIN". Please update all to capital letter. | 2026-03-17 | Ray | Refer to Screen Capture | Bug | P4 |  | Fixed |  | Low |  | Fixed
11 | Engine Type List | UI | Should | None | Sort the engine type list in alphabetical sequence | 2026-03-17 | Ray | Refer to Screen Capture | Enhancement |  |  | Not a bug, to be addressed as new request |  | Low, fixed |  | Fixed
12 | Admin - Template Create - Task Selection | System | Must | None | For Module Level tasks (Items 5, 9, 15, 32, 33, and 39), updating the top‑level item should also update the sub‑tasks automatically. | 2026-03-17 | Edmond | Refer to Screen Capture | None |  |  | No action |  | High, operational risk |  | Fixed
13 | Planner - Tasks | System | Must | Bug | Update Task 4 Finish Date: | 2026-03-16 | Ricky | Refer to Screen Capture | None |  |  | Dev to reproduce issue |  | Low, fixed |  | Fixed
1. 41500 was created on 17 Mar 2026, and Task 4 actual completion date is 17 Mar 2026; however, it is currently showing as 16 Mar 2026.
2. Unable to select “Cancel for Approval.”
14 | Planner - Tasks | System | Must | Bug | Update Task 4 Finish Date: | 2026-03-16 | Ricky | Refer to Screen Capture | None |  |  | Dev to reproduce issue |  | high, operational risk |  | Not yet fix
Job 21231 was completed on 17 May 2026. The completion date was entered as 16 Mar 2026; however, it is not reflected under “Actual Completion.”
2. Unable to select “Cancel for Approval.”
15 | Notification - Line Manager | System | Must | Bug | No items in the line manager notification list even there are few items are pending approval | 2026-03-17 | Ray | Refer to Screen Capture | Bug | P3 |  | Notifications seems to disappear in View All screen |  | high, bug |  | Not yet fix
16 | Input Type | UI | Should | None | Please update the default value to "Engine", currently is "Others". HAESL major business is "Engine". | 2026-03-17 | Ray | N/A | Enhancement |  |  | Changes to be done |  | Low, fixed |  | Fixed
17 | System | System | Must | Bug | Unstable of system access, frequently time out/no response when access the system main page, active streamer page | 2026-03-17 | Ray | Refer to Screen Capture | Bug | P4 |  | Need more details from HAESL on timeout duration and to be verified against NFR |  | high, operational risk |  | Not yet fix
18 | System | System | Should | None | Please remove the "Overview" button if nothing was developed under this page | 2026-03-17 | Ray | Refer to Screen Capture | Enhancement |  |  | To be removed |  | Low, fixed |  | Fixed
19 | Admin - Template Management | System | Must | Bug | When two users edit the same template and press save, system will create two templates with the same name. If we delete either one of them, both of the template will be deleted. Could the system lock the template if it is being edit to solve this problem? | 2026-03-17 | Edmond | Refer to Screen Capture | Bug | P4 |  | Needs to be addressed |  | high, bug |  | Not yet fix
Co-edit issue
20 | Notification | System | Must | Bug | The hour counting is incorrect | 2026-03-17 | Ray | Refer to Screen Capture | Bug | P4 |  | Needs to be addressed |  | Low |  | Fixed
21 | Planner - Create Streamer | System | Must | Bug | When create streamer, module level task was unexpected disabled. | 2026-03-17 | Ray | Refer to Screen Capture | Bug | P4 |  | Need additional information |  | Closed |  | Closed
22 | Admin - Gate Setting, Module Setting & Task Setting | System | Must | Bug | The gate setting or module setting change, the template won't have any update. e.g. I delete the Gate 1B, but the Gate 1B still in the template. All the setting should be synchronize. | 2026-03-17 | Ray | Refer to Screen Capture | None |  |  | As per requirement |  | High |  | Fixed
23 | Tasks | System | Must | Bug | Unexpected error after input ACD for the task and press save. | 2026-03-17 | Ray | Refer to Screen Capture | Bug | P4 |  | Unable to produce bug, Additional information needed |  | high, fixed |  | Fixed
24 | Notification - Line Manager | System | Must | Bug | When I click Accept on an approval task, the approvals list does not refresh immediately to remove the task card. I have to close and reopen the list to see the update. In addition, the task continues to display “Pending for approval”. | 2026-03-17 | Ray | Refer to Screen Capture | Bug | P3 |  | Needs to be addressed |  | medium, operational risk |  | Fixed
25 | Tasks | System | Must | Bug | Unable to cancel for approval when click "Cancel for Approval" button | 2026-03-17 | Ray | Refer to Screen Capture | None |  |  |  |  | High |  | Not yet fix
26 | Tasks | System | Must | Bug | After enter a late PCD, the reason for delay list is nothing inside | 2026-03-17 | Ray | Refer to Screen Capture | Bug | P3 |  | Fixed |  | High, bug |  | Fixed
27 | Tasks - Task Owner Filter | System | Must | Bug | The Task Owner drop-down list is not syncing with the latest Task Owner settings in Admin. Please update the list items and sort them in alphabetical order. | 2026-03-18 | Ray | Refer to Screen Capture | Bug | P4 |  | Needs to be synced |  | Medium, bug |  | Fixed
28 | Streamer - Module Level Task | System | Should | None | The sequence of module level task should follow the module sequence in admin setting | 2026-03-18 | Ray | Refer to Screen Capture | Enhancement |  |  | To be changed as mentioned |  | Medium, performance issues |  | Fixed
29 | Tasks - Task Owner Filter | System | Must | Bug | Duplicate selection items found. | 2026-03-18 | Ray | Refer to Screen Capture | Bug | P4 |  | Needs to be addressed |  | medium, fixed |  | Fixed
30 | Tasks | System | Must | Bug | Planner / Task Owner should not able to disable a task when the task already completed. (L02) | 2026-03-18 | Ray | Refer to Screen Capture | None |  |  | Changes as per L02 |  | medium, fixed |  | Fixed
31 | Tasks - Approval Process | System | Must | Bug | The list of pending approval tasks do not align with the actual pending approval task | 2026-03-18 | Ray | Refer to Screen Capture | Bug | P4 |  | Needs to be addressed |  | High, bug |  | Fixed
Notification - Approval
32 | Admin - Task Selection update | System | Must | Bug | When user update column Start Day and Duration value, system will auto selected the row, it is not what we expect. | 2026-03-18 | Ricky | Refer to Screen Capture | Bug | P4 |  | As per email with Ray, auto selection to be removed |  | medium, operational risk |  | Fixed
33 | Admin - Task Selection update | System | Must | Bug | When user update module level task Start Day and Duration value and save, the value remain the past value in the edit page, but with the update value in the preview page. | 2026-03-18 | Ricky | Refer to Screen Capture | Bug | P4 |  | As per email with Ray, Save should reflect change in the same page |  | medium, bug |  | Fixed
34 | Admin - Task Selection update | System | Must | None |  | 2026-03-18 | Ricky | N/A | Bug | P4 |  | Working as per requirement, module level tasks to be updated manually |  | Removed |  | Closed
35 | Streamer - Induction update | System | Must | Bug | On the streamer page, the induction date shows 19 Mar, which does not match the edit page showing 12 Mar. | 2026-03-18 | Edmond | Refer to Screen Capture | Bug | P4 |  | Needs to be addressed |  | high, fixed |  | Fixed
36 | Planner - Create Streamer / Edit Streamer | System | Must | None | 1.If I press the selection box for module 31 and then press the selection box for module 32, the selection boxes for M31 & M32 will keep showing up | 2026-03-18 | Ming | Refer to Screen Capture | Enhancement |  |  | All modules to be shown as per screenshot, @Ray to confirm the change |  | medium, fixed |  | Fixed
2. Selection box is too small, need to waste time to find the choice, if i click the selection box it can show all options, that will be better.
37 | Admin - Template Edit | UI | Must | rework | Header of Task Selection (Step 2) is hidden and the header text NOT be fit into width of columns | 2026-03-18 | Chris |  | Bug | P4 |  | Needs more details |  | medium, performance issue |  | Not yet fix
38 | Admin - Template Edit / | UI | Must | rework | Content and header is not aligned | 2026-03-18 | Chris |  | Bug | P4 |  | Known issue, Raised with Syncfusion and is pending fix |  | Low, not yet fixed |  | Not yet fix
| Planner - Tasks |  |  |  | Duplicated, Refer to #7
39 | Planner - Menu Side Bar | UI | Must | Bug | The label by the hover effect on the menu button is blocked for the button navigation | 2026-03-18 | Chris |  | Bug | P4 |  | Move the hover text to the side |  | low, fixed |  | Fixed
40 | Planner - Tasks | UI | Must | Bug | The horizontal scroll-bar is hidden on the bottom | 2026-03-18 | Chris |  | Bug | P4 |  | Always show scroll bar |  | medium, operational risk |  | Not yet fix
41 | Admin - Template Edit / | System | Must | Bug | All the fields setting in template should not change even any change happened in the task management. But now when the user go to the edit streamer page, latest task setting will auto update the setting in template edit page. | 2026-03-18 | Edmond | Refer to Screen Capture | None |  |  | As per requirement, BRD 4.2.9 |  | High |  | Fixed
Planner - Tasks
9. Any changes(updating and deleting) in the Tasks management will NOT affect in Templates
42 | Planner -> Streamer -> Active Steamers | System | Must | Rework | Cost / DIW covers Tasks 1 to 15 only. As the inspection date is 07 Mar 2026, | 2026-03-19 | Ricky | Refer to Screen Capture | [5 empty] | Removed |  | Closed
please confirm that the end date should be 07 Mar 2026 rather than 01 Apr 2026.
43 | Planner -> Streamer -> Active Steamers | System | Must | Bug | The Actual Completion Date was completed on 07 Mar 2026, but it is not reflected in the system.(Fxied) | 2026-03-19 | Ricky | Refer to Screen Capture | Bug | P3 |  |  |  | medium, operational risk |  | Not yet fix
Task disable/enable without any confirmation (User need to click save to make changes)
44 | Planner -> Streamer -> Active Steamers | System | Must | Bug | 1. I entered the induction date as 03 Mar 2026; however, it is displaying as 23 Feb 2026. Please advise if incorrect data was entered. | 2026-03-19 | Ricky | Refer to Screen Capture | Bug | P3 |  |  |  | high. Fixed |  | Fixed
2. The induction date cannot be amended to 03 Mar 2026.
45 | Planner -> Streamer -> Create Streamer | System | Must | Bug | Module Set → Sales Order: | 2026-03-19 | Ricky | Refer to Screen Capture | [5 empty] | Removed |  | Closed
Unable to display multiple Sales Orders (S/Os).
Please confirm whether “Trent 1000” is represented as “Trent 100 TEN” in the workscope.
46 | Planner -> Streamer -> Create Streamer | System | Must | Bug | Why can duplicate Sales Orders (S/Os) be displayed? | 2026-03-19 | Ricky | Refer to Screen Capture | [5 empty] | Removed |  | Closed
47 | Planner -> Streamer -> Create Streamer | System | Must | Bug | Issue: When creating Module M33 only, the system still displays other modules in the result/list view. | 2026-03-19 | Ricky | Refer to Screen Capture | [5 empty] | Removed |  | Closed
Note: A valid template is in use; therefore, this issue is unlikely to be template‑related.
48 | Active Streamer > Edit Streamer | System | Must | Bug | Module still in the streamer after remove it in the edit mode and save if the module already removed in the admin setting. | 2026-03-19 | Ray | N/A | Bug | P3 |  | Not clear, please provide steps and additional details |  | Removed |  | Closed
@Ray
49 | Template Management - Edit Template | System | Must | Bug | the template edit page allow double click the fields(Task owner, Start Day, Duration) to access the target fields to do modification, but it is not working. The modification only happen the user update the fields by click the "Edit" Pencil button | 2026-03-19 | Ray | N/A | Bug | P4 |  |  |  | Medium |  | Fixed
50 | Planner -> Streamer -> Amend Streamer | System | Should | Rework | When existing engine streamer module work level change and load a new template or not, all the existing tasks data should be keep. | 2026-03-19 | Ricky | Refer to Screen Capture | None |  |  | Not clear, need understanding @Ray |  | high, operational risk |  | Not yet fix
51 | Planner > Tasks Edit | System | Must | Bug | Once I input non-date on the Acutal Completion Date, PCD is changed unexpected. Please validate if the ACD input is a number | 2026-03-19 | Chris |  | Bug | P4 |  | To be checked |  | high, fixed |  | Fixed
52 | Planner > Streamers | System | Should | Rework | the user just want to cancel one of the filter fields but only one button to "Clear All" | 2026-03-19 | Chris |  | Enhancement |  |  | Currently as per requirement, Please details if any modification required |  | low, performance issue |  | Not yet fix
53 | Edit Streamer | System | Must | Bug | Engine/Module Set multiple sales order for each module, when user edit the streamer all sales order in module become the same sales order | 2026-03-19 | Ray | Refer to Screen Capture | Bug | P3 |  | Fixed |  | high, fixed |  | Fixed
54 | Planner > Streamers | System | Must | Rework | Inconsistent positions on the TRT indication even it can be blocked by the icon | 2026-03-19 | Chris |  | Bug | P3 |  | To be fixed |  | low, display issue |  | Not yet fix
55 | Planner > Streamers | System | Must | Bug | All tasks have the Actual Completion Date entered as 19 Mar 2026, but the system displays 18 Mar 2026. | 2026-03-19 | Ricky | Refer item 56 to Screen Capture | None |  |  | Please provide Streamer details. @Ray, @Ricky |  | High |  | Fixed
56 | Planner > Streamers | System | Should | Rework | The top‑level task has been completed; please proceed to complete the sub‑tasks. Engine Level Task update PCD, all module level task will update too (not included the swap module task) | 2026-03-19 | Ricky | Refer to Screen Capture | [5 empty] | High |  | Not yet fix
57 | Planner > Streamers | System | Must | Bug | For Engine 26121: | 2026-03-19 | Ricky | Refer to Screen Capture | [5 empty] | Removed |  | Closed
Task 6 – Components Receipt at Vendor
The task Finish Date is 25 Mar 2026; however, the Actual Completion Date was updated to 18 Mar 2026 due to early completion.
Task 7 – Parent Task (Components Sentencing)
The Finish Date remains 01 Apr 2026 and was not automatically revised to 25 Mar 2026, despite Task 6 being completed earlier.
58 | Admin - Template Management | Gantt View | Should | Rework | Vertical Scroll Bar is visible all the time but not the horizontal one. Ensure the Horizontal Scroll Bar is visible all the time. | 2026-03-20 | Eugene | Refer to Screen Capture | Enhancement |  |  | To be done |  | medium, performance issue |  | Not yet fix
59 | Admin - Template Management | Gantt View | Should | Rework | The Arrow Line and the Wording of Task Description should not be overlapped | 2026-03-20 | Eugene | Refer to Screen Capture | Bug |  |  | To be done |  | medium, performance issue |  | Not yet fix
60 | Admin - Template Management | Gantt View | Should | Rework | Put a space before and after hypen (-) | 2026-03-20 | Eugene | Refer to Screen Capture | Enhancement |  |  | To be done |  | medium, performance issue |  | Not yet fix
61 | Planner -> Streamer -> Create Streamer | System | Must | Bug | The dispatched Module S/N cannot be changed at the first input. | 2026-03-24 | Ricky | Refer to Screen Capture | None |  |  | Not clear understanding, please provide details @Ricky |  | Removed |  | Closed
Resolved: Click swap module button and click the Set as Default
62 | Admin - Template Management | Gantt View | Should | Rework | Since this is the template's grantt view, the display's start date and end date should be showing number instead of calendar date | 2026-03-24 | Eugene | Refer to Screen Capture | Bug |  |  | To be corrected |  | Low |  | Fixed
63 | Planner -> Streamer -> | System | Must | Bug | Tasks may be completed earlier than anticipated. Attempted to select today's date (25/03/2026), Project Completion Date cell does not allow for dates earlier than 03/04/2026. Why cannot earlier. | 2026-03-24 | Ricky | Refer to Screen Capture | Bug |  |  | To be fixed |  | High |  | Not yet fix
Ray: The date selection in calendar in both PCD and ACD is not consistent, sometimes could input today -7, sometimes could input today -14.
64 | Notification | System | Must | Bug | When there are no pending approval tasks, the approval notification icon displays system update logs. We expect the system to display nothing when there are no approval items for Approval Icon. | 2026-03-27 | Ray | Refer to Screen Capture | Bug |  |  |  |  | medium, operational risk |  | Fixed
65 | Task Update | System | Must | Bug | Parent Child Relationship do not cover all current practises | 2026-03-27 | Eugene | N/A | Bug | P4 |  | To be verified |  | High, bug |  | Not yet fix
1. WHEN Parent PCD + 2 days, THEN Child PCD + 2 days - Success
2. WHEN Parent PCD - 2 days, THEN Child PCD - 2 days - Failure
3. WHEN Parent ACD + 2 days, THEN Child PCD + 2 days - Failure
4. WHEN Parent ACD - 2 days, THEN Child PCD - 2 days - Failure
66 | Test Plan | System | Must | Bug | Fail to upload test plan. When click the preview button, system error prompt | 2026-04-01 | Ray | Refer to Screen Capture | Bug | P3 |  |  |  | High, bug |  | Not yet fix
67 | Task Update | System | Must | Bug | Text in the "Comments" disappeared after save | 2026-04-01 | Ray | Refer to Screen Capture | Bug | P4 |  |  |  | High, bug |  | Not yet fix
68 | Task Update | System | Must | Bug | what is the max length of reject reason? System error when the reason is a long text | 2026-04-01 | Ray | N/A | Bug | P4 |  |  |  | medium, operational risk |  | Not yet fix
69 | Notification - Approval | System | Must | Bug | In the view all page, Line manager section. Expected Completion Date means Projected Completion Date? if yes, please update. And please add the column of "Actual Completion Date" in this table too. | 2026-04-01 | Ray | Refer to Screen Capture | Enhancement |  |  |  |  | low, display issue
70 | Admin -> Streamer settings -> Task Owner Settings | System | Must | Bug | Task Owner setting cannot be saved for more than two users. | 2026-02-04 | Ricky | Refer to Screen Capture | Bug | P1 |  | Fixed |  | medium, fixed
E.g. add user to line manager or user, unable to click the "Save" button
71 | Task Update | System | Must | Bug | L02 - Task Enable/Disabled : User needs to click on save button | 2026-04-02 | Praveen on Ray's Behalf |  | Bug | P4 |  | Enable/Disable to make the change and click on save. To be fixed in Patch 2 |  | Low
72 | Task Update | System | Must | Bug | L03 - Complete to WIP, Line manager approval needed | 2026-04-02 | Praveen on Ray's Behalf |  | Bug | P3 |  | To be fixed in Patch 1 - Apr4 |  | High
73 | Task Screen | System | Must | Bug | U04 - Interface issue - Window not moveable | 2026-04-02 | Praveen on Ray's Behalf |  | Bug | P4 |  | To be fixed in Patch 2 |  | Medium
74 | Task Screen | System | Must | Bug | U09 - Custom Date Range filter | 2026-04-02 | Praveen on Ray's Behalf |  | Bug | P3 |  | Syncfusion currently doesnt support it, raised a ticket for resolution. Only Month view available as per calendar |  | Medium
75 | Task Screen | System | Must | Bug | U12 - Task Screen : Hard to identify streamer and task | 2026-04-02 | Praveen on Ray's Behalf |  | Bug | P4 |  | Syncfusion doesn’t support 2 columns. Font size of the Streamer name to be increased with Streamer name in bold |  | Medium
76 | Test Slot | System | Must | Bug | F01. Test Plan Upload fails intermittently | 2026-04-02 | Praveen on Ray's Behalf |  | Bug | P3 |  | We are looking into this and are trying to reproduce this, will be addressed in Patch 1 |  | High
77 | Task Screen | System | Must | Bug | U12 - Task Screen : Hard to identify streamer and task | 2026-04-02 | Praveen on Ray's Behalf |  | Bug | P4 |  |  |  | Removed |  | Closed
Duplicated, refer to #75
78 | Task Screen | System | Must | Bug | F03 - all the input in the comments box disappeared after save | 2026-04-02 | Praveen on Ray's Behalf |  | None |  |  | Not a bug, works as expected |  | High
79 | Line Manager | System | Must | Bug | F05 - Line manager rejects a back date entry requires reject reason - System error when type a long text reject reason | 2026-04-02 | Praveen on Ray's Behalf |  | Bug | P4 |  | Fixed and will be available in Patch 1 |  | High
80 | Streamer | System | Must | Bug | F08. “Edit Streamer” button FAIL, when reload a template, all previous template COMPLETED tasks data should be fill in to the NEW template | 2026-04-02 | Praveen on Ray's Behalf |  | Bug |  |  | Re-induction will only contain tasks from newly selected template, all old tasks will be part of previous issue |  | High
81 | Module Swap | System | Must | Bug | F09 - . Module swap assistance FAIL, same module cannot swap to more than one engine streamer at the same time. Module could swap from Engine A then Engine B, but not Engine A and Engine B. | 2026-04-02 | Praveen on Ray's Behalf |  | Bug | P3 |  | Fixed after we received feedback during Demo 3. Will be available in Patch 1 |  | High
82 | Admin -> Template Management -> Amendment | System | Must | Bug | The Task Owner update cannot be changed to another section code. | 2026-03-04 | Ricky | Refer to Screen Capture | Bug | P3 |  | Changes reflects in review screen but if the user goes back to the screen then the changes not reflected, Issue fixed and pending deployment |  | Medium |  | Fixed
For example, after clicking “Save” and returning to review, no change is reflected.
83 | Admin -> Template Management | System | Must | Bug | Tasks 11, 16, 21, and 25 are hidden and can't add back | 2026-04-03 | Ricky | Refer to Screen Capture | Bug | P1 |  | Bug. fixed |  | High |  | Fixed
84 | Streamers->create streamer | System | Should |  | No error message is shown when mandatory input data is missing. | 2026-04-06 | Edmond | Refer to Screen Capture | None |  |  | No error message will be shown but wont let the user proced further without filling the mandatory fields the uesr cannot proceed further |  | Removed |  | Closed
85 | Streamers->create streamer | System | Should |  | Can't type induction date. | 2026-04-06 | Edmond | Refer to Screen Capture | None |  |  | User needs select from Date picker as per design. Manual entry can cause format inconsistency and errors |  | Removed |  | Closed
86 | Streamers->create streamer | System | Should |  | if create error template (engine template /module template ) can't change to Module template from Engine Template | 2026-04-06 | Edmond | Refer to Screen Capture | None |  |  | Need more details from HAESL |  | Removed |  | Closed
[5 empty] | Ray: there are no input type template classification in system, issue closed | [6 empty] | @Ray
87 | Streamers->create streamer | System | Should |  | When creating a TRT, if “Engine” is selected as the input type, it should accept numbers only. There should be validation to check whether any incorrect (non‑numeric) input is entered. | 2026-04-06 | Edmond | Refer to Screen Capture | Bug | P4 |  | Engine validation required |  | Removed |  | Closed
[5 empty] | For system flexibity, this validation is not necessary at this moment, issue closed | [6 empty] | @Ray
88 | Streamers->create streamer | System | Should |  | 1.It is not possible to change only the streamer name. | 2026-04-06 | Edmond | Refer to Screen Capture | Enhancement |  |  | Streamer name change is what type @Ray |  | Removed |  | Closed
2. after update streamer name .the streamer name didn't change.
Ray: template name is generate by a default format and not suppose for edit, issue closed
89 | Streamers-> Task | System | Should |  | 1.In the Task section, only tasks that have not yet been entered should be displayed. | 2026-04-06 | Edmond | Refer to Screen Capture | None |  |  | Not clear @Ray |  | Medium |  | Not yet fix
2.after update actual date and save .tarage Engine should not close
90 | Streamers-> Task | System | Should |  | no print function in task section | 2026-04-06 | Edmond | Refer to Screen Capture | None |  |  | Not a requirement |  | Removed |  | Closed
TBD
91 | Streamers->create streamer | System | Should |  | can't delete error template | 2026-04-06 | Edmond | Refer to Screen Capture | None |  |  | Screenshot missing, needs additional details @Ray |  | Removed |  | Closed
TBD
92 | Planner - Create Streamer | System | Must | Bug | 1. The “Dispatch Module S/N” cannot be changed (again). | 2026-04-06 | Ricky | Refer to Screen Capture | None |  |  | 1. Dispatch module is not editable as text. It should be selected from off-module list |  | Low
[5 empty] | 2. Please add a Back function next to Save. | [6 empty] | 2. As per design
[5 empty] | 3. Please sort the “Module ATA”. | [6 empty] | 3. In Create Streamer page, it is sorted as per Module ATA and it needs to be sorted in Preview screen
93 | Planner - Create Streamer | UI |  | UI | There is an issue with the date display order. | 2026-04-06 | Edmond | Refer to Screen Capture | None |  |  | As per requirements, user can click on the Test Date filter and sort accordingly |  | Removed |  | Closed
TBD
94 | Planner - Create Streamer | System | Should | Bug | Task Selection → Task Owner (Create & Review pages): | 2026-04-06 | Ricky | Refer to Screen Capture | Bug | P4 |  | Template Create and review is not the same after changes |  | High, bug
The data shown does not match.
95 | Planner -> Engine Update | System |  |  | How to Use the "Offset Module" Function | 2026-04-06 | Ricky |  | None |  |  |  |  | Removed |  | Closed
96 | Planner - Task | System | Must |  | 1. Please add a checkbox to select Not Complete tasks. | 2026-04-06 | Ricky | Refer to Screen Capture | Enhancement |  |  | 1. Task Status can be added as filter in the Task screen @Ray - need your acceptance |  | Medium
2. Do not hide the task.
[5 empty] | 3. How can the Not Complete tasks be printed out? | [6 empty] | 2. Need additional details
3. Print option in task screen not part of requirement
97 | Planner - Create and Amend | System | Must |  | Task 10 & Task 15 – Task Owner Logic | 2026-04-06 | Ricky |  | Enhancement |  |  | Not covered in the requirement |  | High, operational risk
Module Level Task Owner
If Module is L3 or L4, then Task Owner = Bench
If Module Is L1 or L2, then Task Owner = Module Repair
(except for Module 34 which the task owner always be Module Change regardlesss of L1, L2, L3 or L4)
Engine Level Task Owner
If any of the Module Level task owner is Bench, then the Engine Level task owner is Bench
If the Active Module task owner consist both Module Repair or Module Chnage (for Module 34), then the Engine Level task owner is Module Repair
If the Active Module task owner consist only Module Repair, then the Engine Level task owner is Module Repair
If the only Active Module task owner is Module Change (for Module 34), then the Engine Level task owner is Module Change (If only M34 active, Task 10 not active)
If none of the Module is active, then the Engine Level is also not active
Note. Module is not active when work level is L1, New, S/Rec'd
Applicable Modules
M31, M32, M33, M34, M41, M51, M52, M61, Engine Mount
New or S/R Status
Blank or MR
98 | Planner - Task | System | Must |  | Table line not match | 2026-04-07 | Edmond | Refer to Screen Capture | Bug | P4 |  | Syncfusion issue, working with them |  | low, not yet fixed
Duplicated, Refer to #7
99 | Tasks | System | Must | Enhancement | Add task status filter in the page, planner/task owner could select WIP/Disabled/Completed to filter the task list | 2026-04-08 | Ray | N/A | Enhancement |  |  |  |  | Medium, operational risk
100 | Tasks | System | Must |  | Add toggle button to expand the task list for each streamer | 2026-04-08 | Ray | N/A | Enhancement |  |  | Toggle button attribute @Ray |  | Low
101 | User access | System | Must | None | Staff/Task Owner only able to view Streamer and Tasks | 2026-04-09 | Ray | N/A | Enhancement |  |  | As per requirement |  | low, fixed
102 | Tasks | System | Must | Enhancement | Add Task Name and Sales Order no. on task editing page | 2026-04-09 | CCB | N/A | Enhancement |  |  |  |  | Medium, operational risk
103 | Notification | System | Must | Enhancement | Notification does not have sufficient information (e.g. Sales Order, ESN, what has been updated etc.) | 2026-04-09 | CCB | N/A | Enhancement |  |  | Please mention which details are needed with a few sample messages @Ray |  | Medium, operational risk
104 | Tasks | System | Must | Enhancement | Add Task Status filter in Task view page to fiter WIP/Disabled/Completed task status | 2026-04-09 | Logistics | N/A | Enhancement |  |  | Duplicate 99 |  | Medium, operational risk
105 | Tasks | System | Must | Enhancement | Monthly filter is not user friendly to view all task belong to me. Could the duration become unlimited to show all date? | 2026-04-09 | Logistics | N/A | Enhancement |  |  | Provide exact requirement, Do you want a see Quarter or Yearly view? With all duration, the tasks will be not be visible @Ray |  | Medium, performance issue
106 | Admin - Task Management | System | Must | Bug | For the XWB97 HSV Template, | 2026-04-09 |  | Refer to Screen Capture | Bug |  |  |  |  | High, operational risk
a mismatch has again been identified between the amendment pages and the displayed data for Tasks 15, 32, and 33.
107 | Tasks | System | Must | Enhancement | Task Owner should not able to input futher date within a date range | 2026-04-09 | CCB |  | Enhancement |  |  | Please provide exact requirement @Ray |  | Medium, operational risk
108 | Tasks | System | Must | Enhancement | My Tasks display format not user friendly. Cannot only focus with the outstanding issues. With Searching result : SP, Task 35, 84K, but still showing full Calendar date with no outstanding Task 35. And should not need to click each engine for checking if any outstanding. | 2026-04-09 | SP |  | Enhancement |  |  | Please provide the expected enhancement requirement @Ray |  | Medium, operational risk
109 | Create Streamer | System | Must | None | All "Dispatch Module S/N" set to RETAIN, remove the "Set to Default" button in swap module pop up page | 2026-04-09 | Ray | N/A | None |  |  |  |  | Medium, design fault
110 | User Setting | System | Must | Bug | Unable to search the user from the access right list after add the user, and the user unable to access the streamer too. | 2026-04-10 | Ray | Refer to Screen Capture | Bug | P1 |  | Being worked on |  | High, bug
111 | Notification | System | Must | Bug | By clicking both Approval icon or Notification icon, the system only shows the approval request information. | 2026-04-10 | Ray | N/A | Bug |  |  |  |  | High,. Bug
112 | Tasks | System | Must | None | Actual Completion Date Should not allow user to select future date. User only able to select today or back date. | 2026-04-13 | Ray | N/A | Enhancement |  |  |  |  | Medium, operational risk
113 | Tasks | System | Must | Bug | cw-ray.lam@haesl.com not belong to any task owner dept, why I could update any task data, and do the approval? | 2026-04-13 | Ray | N/A | [5 empty] | Medium, bug
114 | Notification-Line Manager | System | Must | None | The View all page of Line Manager should show the approved by and approved date column, some dept may have more than one line manager. | 2026-04-13 | Ray | N/A | Enhancement |  |  |  |  | Medium, informational clarity
115 | Task | System | Must | None | Only Planner could disable task (TBC) | 2026-04-14 | Ray | N/A | [5 empty] | Medium, operational risk
116 | Notification - Action Log | System | Must | Rework | Action log does not show complete information (e.g. cannot show which category has been changed, which ESN, which S/O). | 2026-04-14 | various | N/A | [5 empty] | Medium, multiple issues
Able to clear all notification by a button.
And categorize the action log e.g. filter of task update action, filter of test plan update action, notify delayed task if the task WIP. if the action log is about task, user could click on the notification and redirect to the tasks details pop-up screen
If too much infomation in each action log, could default collapse and user click on the log will become expand?
117 | Template - task selection | System | Must | Rework | In task selection page, the header row should be frozen | 2026-04-14 | Ray | Refer to Screen Capture | [5 empty] | Low, bug
118 | Template - task selection | System | Must | Bug | When I edit a task details (e.g. task owner), after I confirm the screen will focus to other area. | 2026-04-14 | Ray | N/A | [5 empty] | Medium, the position of the form should be sticky after action triggered
119 | Task | System | Must | Bug | After actual completion date updated, no log display for the change | 2026-04-14 | CR | N/A | [5 empty] | Medium, bug
120 | re-induction | System | Must | Rework | DIW and cost review streamer can be re-induction day back day within 7 day | 2026-04-14 | Ray | N/A | [5 empty] | Medium, bug
121 | streamer -> task (aw approval) | System | Must | Bug | some awaiting approve task click enabled button than click the cancel for approval.whatever the task input the ACD and the task will be disabled | 2026-04-14 | Ray | N/A | [5 empty] | Medium, bug
122 | streamer -> task | System | Must | Rework | task action log unclear.the comments commented by last user should stay in comments box. | 2026-04-14 | Ray | N/A | [5 empty] | Medium
123 | Streamer > Export | System | Should | Enhancement | No matter for PDF or CSV file, to enhance information exported for below columns included: | 2026-04-15 | Chris | [6 empty] | Low, but performance issue
¦ Streamer Name ¦ ESN ¦ Sales Order ¦ Visit Type ¦ Customer Code ¦ Input Type ¦ Induction Date ¦ Test Date ¦ Status (WIP/Completed/Disabled) ¦
124 | Streamer > Edit Streamer > Export | System | Should | Enhancement | No matter for PDF or CSV file, to enhance information exported for below columns included: | 2026-04-15 | Chris | [6 empty] | Low, but performance issue
¦ Task No ¦ Task Name ¦ Task Owner ¦ Duration ¦ Start Date ¦ Finish Date ¦ Projected Completion Date ¦ Actual Completion Date ¦
125 | Tasks Page > Export | System | Should | Enhancement | To align with Export function with Streamer page, to add Export to PDF & CSV and generate the columns included: | 2026-04-15 | Chris | [6 empty] | Low, but performance issue
¦ Task Owner ¦ Task ID ¦ Duration ¦ Start Date ¦ Finish Date ¦ Projected Completion Date ¦ Actual Completion Date ¦ Induction Date ¦ Test Date ¦ Reason of Delay ¦ Comments ¦ Task status (WIP/Completed/Disabled) ¦
126 | Off-module list > Export | System | Should | Enhancement | To align with other export function, please add the export to PDF & CSV with the columns included: | 2026-04-15 | Chris | [6 empty] | Low, but performance issue
¦ Module Name ¦ Module Status ¦ Module ATA ¦ Module SN ¦ Work Level ¦ Engine Type ¦ Cust. Code ¦ Sales Order ¦ Induction Date ¦ Module Build Date ¦ To ESN ¦ Ex ESN ¦ Return to Cust ¦ Reduce to Parts ¦
127 | Test Slot | System | Must | Bug | 21954 Test Plan Excel File showes 05/Jun. After test plan file upload, the Project Completion Date of Task 39 - Test (MST) still unchanged on 11/May | 2026-04-15 | Eugene | [6 empty] | High, critical bug
128 | Streamer > Streamer Edit Page | System | Must | Bug | it cannot be refreshed by "Refresh (Ctrl + R)" | 2026-04-15 | Chris | [6 empty] | Low, bug
129 | Test-slot > Upload | System | Must | Enhancement | For Task Owner & Staff, the function called "Upload" should be not provided. | 2026-04-15 | Chris | [6 empty] | Medium, operational risk
130 | Test Slot Preview | System | Must | Bug | The remark is not correct. For example the engine is in test plan but the remark's comment said the engine is not in the test plan. | 2026-04-15 | Eugene | [6 empty] | High, bug
131 | Task Owner > Task Update | System | Must | Bug | Request to remove Actual Complation Date and request for approval was sent and approved. The Actual Completion still not removed. | 2026-04-16 | Eugene | [6 empty] | High, bug
132 | DIW,cost review streamer | System | Must | Bug | 1. DIW completed and released, streamer then change to Cost Review and will need to capture second release date for Cost Review. | 2026-04-16 | Ricky | [6 empty] | High
2. The DIW streamer cannot be converted to a normal streamer as non-DIW tasks are still locked (Grey Color).
3. The Cost Review streamer cannot be converted to a normal streamer as non-Cost Review tasks are still locked (Grey Color). Also the Cost Review Task data such as Finish Date, PCD & ACD should not be changed (Same as Cost Review Streamer) except for Task 4 Inducton
133 | Task Owner - Tasks | System | Must | Bug | The tasks view always have unexpected movement of the user view. When I click on a task at the bottom, after I save the task to view the changes, the screen will move back to the top of the calendar, not orginally I focus on. | 2026-04-17 | Ray | To be demo | [5 empty] | Medium, the position of the form should be sticky after action triggered
134 | Tasks | System | Must | Rework | Task action log not really record all the changes, e.g. not record the delay reason, not record the PCD date changes | 2026-04-17 | Various | Refer to screen capture | [5 empty] | Low
135 | Notification | System | Must | Bug | In the view all page, we found that the date column in the date format, user can not sort the data by date, please check all the column data type | 2026-04-17 | Ricky | N/A | [5 empty] | Low
136 | Tasks | System | Should | Rework | Add "Other Reason" in the delay reason dropdown list | 2026-04-17 | CCB | N/A | [5 empty] | Low
137 | Notification - Approval Task | System | Should | Rework | For Task approval Line manager require more information to take action, missing sales order, not declare it is a backdate approval or ACD change approval, missing task name. Could system redirect to the task pop up by clicking on the approval notification? Remove the "X" in approval notification list, to avoid Line manager skip/missing any pending approval task. | 2026-04-17 | Various | N/A | [5 empty] | High, operational risk
138 | Tasks | System | Must | Rework | As a task owner, currently design is not user-friendly, I can not focus on any WIP tasks belong to my department. Suggest to add below filters: | 2026-04-17 | Various | N/A | [5 empty] | Medium
Task PCD in Today/This Week/Overdue
139 | Notification | System | Should | Rework | Each notification allow me to redirect to the corresponding streamer/task for follow up | 2026-04-17 | Various | N/A | [5 empty] | Medium, operational risk
140 | Tasks | System | Must | Rework | As a task owner, I also need to know the below infomation in the task pop up | 2026-04-17 | Various | N/A | [5 empty] | Low
ESN, Module S/N(if it is a module level task), Task Name, Sales Order, Task Owner, Streamer Status. Add an area to shows all streamer tasks status.
141 | Active Streamer | System | Must | Rework | Not Able to search the streamer by module S/N | 2026-04-17 | CR | N/A | [5 empty] | Medium
142 | Tasks | System | Must | Rework | As a task owner, how could I know the pending approval task was approved or rejected? | 2026-04-17 | Various | Refer to screen capture | [5 empty] | Medium, not notify the requester
143 | Active Streamer | System | Must | Rework | In the streamer page to view all the tasks for streamer, column name "Actual Finish Date" should be "Actual Completion Date" | 2026-04-17 | Ray | Refer to screen capture | [5 empty] | Low
144 | Active Streamer | System | Must | Bug | Unable to select or view previous issue of streamer | 2026-04-17 | Ray | N/A | [5 empty] | Medium
145 | Planner -> Streamer | System |  | Rework | HAESL Visit Type: no RTP | 2026-04-18 | Ricky | [6 empty] | Medium
146 | Planner -> Streamer | System |  | Rework | Task 9, (10), 15, 32, 33 – Task Owner Logic | 2026-04-18 | Ricky | [6 empty] | High, engine task is not aligned with module
If Tasks 9, (10), 15, 32, and 33 are all at Level 1 (L1) and disabled at the module level, please also disable the engine level.
If a module is upgraded from Level 1 (L1) to Level 2 (L2), the corresponding applicable items shall be enabled.
147 | Planner -> Streamer | System | Must | Bug | Module SN change only – task data (Finish Date, PCD, ACD) to remain unchanged. | 2026-04-18 | Ricky | [6 empty] | High, operational risk
Duplicted, refer to #50

## classifications
Category | Desciption | Appearance
Swap Module | it is related to the off-module list to interact with the active streamer. In practice terms, the module can be selected from the off-module list to swap into the existing engine streamer on the Streamer Section as a planner role. | 7
Task Owner View | it is all about tasks allocated from the streamer and give the task owner to control their own tasks on the calendar view on task section. They can change the projected completion date (PCD), input actual completion date (ACD) with delayed reasons if any as well as request and approve the request if any trigger is needed. | 5
Notification | On Notification, there are two area for notifying the task owners. Firstly, it is general message notfiication from the task actions like changing the task date from different planner or task owners. Another notification type is to notify the line manager as a supper task owner to accept or reject the approval requests from the staff under the same department group. | 25
DIW/Cost Review | In specific streamer arrangement, the template with the label of DIW/Cost Review can be selected. Once the status of the active streamer is under the status of DIW/Cost Review, the planner would release the investigation or quotation after all tasks are completed in the first induction. Therefore, the planner is able to re-input the second induction information later on. | 4

## calc
Category | Critical Priority | Appearance
Swap Module | Low | 2
| Medium | 2
| High | 2
Task Owner View | Low | 1
| Medium | 3
| High | 1
Notification | Low | 5
| Medium | 11
| High | 9
DIW/Cost Review | Low | 0
| Medium | 1
| High | 2
39

## wiki
Item No. | Section | Issue | MoSCoW | Issue Type (None/Bug/Rework/Enhancement) by HAESL | Comments (Consolidated) | Issue Raise Date | Raised by | Screen Capture | Issue Type (None/Bug/Rework/Enhancement) by RR | Priority Classification (by RR) | User Story No (by RR) | Comments (by RR) (Consolidated) | Change Request Accepted by HAESL(For Enhancements Only) | HAESL Comments (Consolidated) | Comment date, Commented by | Closed/Fixed/Not yet fix | Category | Classification Hint | Critical Priority
42 | Planner -> Streamer -> Active Steamers | System | Must | Rework | Cost / DIW covers Tasks 1 to 15 only. As the inspection date is 07 Mar 2026, please confirm that the end date should be 07 Mar 2026 rather than 01 Apr 2026. | 2026-03-19 | Ricky | Refer to Screen Capture | 0 | 0 | 0 |  | 0 | Removed | 0 | Closed | DIW/Cost Review | diw | Removed
80 | Streamer | System | Must | Bug | F08. “Edit Streamer” button FAIL, when reload a template, all previous template COMPLETED tasks data should be fill in to the NEW template | 2026-04-02 | Praveen on Ray's Behalf | 0 | Bug | 0 | 0 | Re-induction will only contain tasks from newly selected template, all old tasks will be part of previous issue | 0 | High | 0 | 0 | DIW/Cost Review | re-induction | High
120 | re-induction | System | Must | Rework | DIW and cost review streamer can be re-induction day back day within 7 day | 2026-04-14 | Ray | N/A | 0 | 0 | 0 | 0 | 0 | Medium, bug | 0 | 0 | DIW/Cost Review | diw | Medium
132 | DIW,cost review streamer | System | Must | Bug | 1. DIW completed and released, streamer then change to Cost Review and will need to capture second release date for Cost Review. 2. The DIW streamer cannot be converted to a normal streamer as non-DIW tasks are still locked (Grey Color). 3. The Cost Review streamer cannot be converted to a normal streamer as non-Cost Review tasks are still locked (Grey Color). Also the Cost Review Task data such as Finish Date, PCD & ACD should not be changed (Same as Cost Review Streamer) except for Task 4 Inducton | 2026-04-16 | Ricky | 0 | 0 | 0 | 0 |  | 0 | High | 0 | 0 | DIW/Cost Review | diw | High
4 | Notification | System | Must | Bug | Unable to clear notifcations from notifcation list. After clicking the "X", the same notifcation will pop up again later, all the notifications become accumulate as a huge list. | 2026-03-16 | Ray | Refer to Screen Capture | None | 0 | 0 | Not able to reproduce in dev | 0 | Low, but the counter of msg delayed | 0 | Fixed | Notification | notification | Low
13 | Planner - Tasks | System | Must | Bug | Update Task 4 Finish Date: 1. 41500 was created on 17 Mar 2026, and Task 4 actual completion date is 17 Mar 2026; however, it is currently showing as 16 Mar 2026. 2. Unable to select “Cancel for Approval.” | 2026-03-16 | Ricky | Refer to Screen Capture | None | 0 | 0 | Dev to reproduce issue | 0 | Low, fixed | 0 | Fixed | Notification | approval | Low
14 | Planner - Tasks | System | Must | Bug | Update Task 4 Finish Date: Job 21231 was completed on 17 May 2026. The completion date was entered as 16 Mar 2026; however, it is not reflected under “Actual Completion.” 2. Unable to select “Cancel for Approval.” | 2026-03-16 | Ricky | Refer to Screen Capture | None | 0 | 0 | Dev to reproduce issue | 0 | high, operational risk | 0 | Not yet fix | Notification | approval | high
15 | Notification - Line Manager | System | Must | Bug | No items in the line manager notification list even there are few items are pending approval | 2026-03-17 | Ray | Refer to Screen Capture | Bug | P3 | 0 | Notifications seems to disappear in View All screen | 0 | high, bug | 0 | Not yet fix | Notification | notification | high
20 | Notification | System | Must | Bug | The hour counting is incorrect | 2026-03-17 | Ray | Refer to Screen Capture | Bug | P4 | 0 | Needs to be addressed | 0 | Low | 0 | Fixed | Notification | notification | Low
24 | Notification - Line Manager | System | Must | Bug | When I click Accept on an approval task, the approvals list does not refresh immediately to remove the task card. I have to close and reopen the list to see the update. In addition, the task continues to display “Pending for approval”. | 2026-03-17 | Ray | Refer to Screen Capture | Bug | P3 | 0 | Needs to be addressed | 0 | medium, operational risk | 0 | Fixed | Notification | notification | medium
25 | Tasks | System | Must | Bug | Unable to cancel for approval when click "Cancel for Approval" button | 2026-03-17 | Ray | Refer to Screen Capture | None | 0 | 0 | 0 | 0 | High | 0 | Not yet fix | Notification | approval | High
31 | Tasks - Approval Process | System | Must | Bug | The list of pending approval tasks do not align with the actual pending approval task | 2026-03-18 | Ray | Refer to Screen Capture | Bug | P4 | 0 | Needs to be addressed | 0 | High, bug | 0 | Fixed | Notification | approval | High
64 | Notification | System | Must | Bug | When there are no pending approval tasks, the approval notification icon displays system update logs. We expect the system to display nothing when there are no approval items for Approval Icon. | 2026-03-27 | Ray | Refer to Screen Capture | Bug | 0 | 0 | 0 | 0 | medium, operational risk | 0 | Fixed | Notification | notification | medium
68 | Task Update | System | Must | Bug | what is the max length of reject reason? System error when the reason is a long text | 2026-04-01 | Ray | N/A | Bug | P4 | 0 | 0 | 0 | medium, operational risk | 0 | Not yet fix | Notification | reject reason | medium
69 | Notification - Approval | System | Must | Bug | In the view all page, Line manager section. Expected Completion Date means Projected Completion Date? if yes, please update. And please add the column of "Actual Completion Date" in this table too. | 2026-04-01 | Ray | Refer to Screen Capture | Enhancement | 0 | 0 | 0 | 0 | low, display issue | 0 | 0 | Notification | notification | low
70 | Admin -> Streamer settings -> Task Owner Settings | System | Must | Bug | Task Owner setting cannot be saved for more than two users. E.g. add user to line manager or user, unable to click the "Save" button | 2026-02-04 | Ricky | Refer to Screen Capture | Bug | P1 | 0 | Fixed | 0 | medium, fixed | 0 | 0 | Notification | line manager | medium
72 | Task Update | System | Must | Bug | L03 - Complete to WIP, Line manager approval needed | 2026-04-02 | Praveen on Ray's Behalf | 0 | Bug | P3 | 0 | To be fixed in Patch 1 - Apr4 | 0 | High | 0 | 0 | Notification | line manager | High
79 | Line Manager | System | Must | Bug | F05 - Line manager rejects a back date entry requires reject reason - System error when type a long text reject reason | 2026-04-02 | Praveen on Ray's Behalf | 0 | Bug | P4 | 0 | Fixed and will be available in Patch 1 | 0 | High | 0 | 0 | Notification | line manager | High
103 | Notification | System | Must | Enhancement | Notification does not have sufficient information (e.g. Sales Order, ESN, what has been updated etc.) | 2026-04-09 | CCB | N/A | Enhancement | 0 | 0 | Please mention which details are needed with a few sample messages @Ray | 0 | Medium, operational risk | 0 | 0 | Notification | notification | Medium
111 | Notification | System | Must | Bug | By clicking both Approval icon or Notification icon, the system only shows the approval request information. | 2026-04-10 | Ray | N/A | Bug | 0 | 0 | 0 | 0 | High,. Bug | 0 | 0 | Notification | notification | High
113 | Tasks | System | Must | Bug | cw-ray.lam@haesl.com not belong to any task owner dept, why I could update any task data, and do the approval? | 2026-04-13 | Ray | N/A | 0 | 0 | 0 | 0 | 0 | Medium, bug | 0 | 0 | Notification | approval | Medium
114 | Notification-Line Manager | System | Must | None | The View all page of Line Manager should show the approved by and approved date column, some dept may have more than one line manager. | 2026-04-13 | Ray | N/A | Enhancement | 0 | 0 | 0 | 0 | Medium, informational clarity | 0 | 0 | Notification | notification | Medium
116 | Notification - Action Log | System | Must | Rework | Action log does not show complete information (e.g. cannot show which category has been changed, which ESN, which S/O). Able to clear all notification by a button. And categorize the action log e.g. filter of task update action, filter of test plan update action, notify delayed task if the task WIP. if the action log is about task, user could click on the notification and redirect to the tasks details pop-up screen If too much infomation in each action log, could default collapse and user click on the log will become expand? | 2026-04-14 | various | N/A | 0 | 0 | 0 |  | 0 | Medium, multiple issues | 0 | 0 | Notification | notification | Medium
121 | streamer -> task (aw approval) | System | Must | Bug | some awaiting approve task click enabled button than click the cancel for approval.whatever the task input the ACD and the task will be disabled | 2026-04-14 | Ray | N/A | 0 | 0 | 0 | 0 | 0 | Medium, bug | 0 | 0 | Notification | approval | Medium
131 | Task Owner > Task Update | System | Must | Bug | Request to remove Actual Complation Date and request for approval was sent and approved. The Actual Completion still not removed. | 2026-04-16 | Eugene | 0 | 0 | 0 | 0 | 0 | 0 | High, bug | 0 | 0 | Notification | approval | High
135 | Notification | System | Must | Bug | In the view all page, we found that the date column in the date format, user can not sort the data by date, please check all the column data type | 2026-04-17 | Ricky | N/A | 0 | 0 | 0 | 0 | 0 | Low | 0 | 0 | Notification | notification | Low
137 | Notification - Approval Task | System | Should | Rework | For Task approval Line manager require more information to take action, missing sales order, not declare it is a backdate approval or ACD change approval, missing task name. Could system redirect to the task pop up by clicking on the approval notification? Remove the "X" in approval notification list, to avoid Line manager skip/missing any pending approval task. | 2026-04-17 | Various | N/A | 0 | 0 | 0 | 0 | 0 | High, operational risk | 0 | 0 | Notification | notification | High
139 | Notification | System | Should | Rework | Each notification allow me to redirect to the corresponding streamer/task for follow up | 2026-04-17 | Various | N/A | 0 | 0 | 0 | 0 | 0 | Medium, operational risk | 0 | 0 | Notification | notification | Medium
142 | Tasks | System | Must | Rework | As a task owner, how could I know the pending approval task was approved or rejected? | 2026-04-17 | Various | Refer to screen capture | 0 | 0 | 0 | 0 | 0 | Medium, not notify the requester | 0 | 0 | Notification | notification | Medium
2 | Admin - Template Management | UI | Must | Bug | Please remove "Hospital", "Check & Repair", "1st Refurbishment", "2nd Refurbishment", "Mature Refurbishment" from the dropdown list. Add "OH" in the list | 2026-03-16 | Ray | Refer to Screen Capture | Bug | P4 | 0 | Entries to be removed | 0 | Low, no issue now | 0 | Fixed | Other / General | (no match) | Low
3 | Admin - Gate Setting | System | Must | Bug | Unable to show gate "1A" after create. | 2026-03-16 | Ray | Refer to Screen Capture | Bug | P4 | 0 | Suspecting this can be observed when two users performing same operation at atime. Not able to reproduce it in dev by single user | 0 | Low, no issue now | 0 | Fixed | Other / General | (no match) | Low
5 | Planner - Create Streamer | System | Must | Bug | Induction date cannot be backdated. | 2026-03-16 | Ricky | Refer to Screen Capture | Bug | P2 | 0 | Fixed | 0 | Medium, not fixed | 0 | Unstable Fix | Other / General | (no match) | Medium
10 | Planner - Create Streamer / Edit Streamer | System | Must | None | Inconsistency of value "Retain", if the row added by user, system shows "Retain", if the row is recongnise by PDF, system show "RETAIN". Please update all to capital letter. | 2026-03-17 | Ray | Refer to Screen Capture | Bug | P4 | 0 | Fixed | 0 | Low | 0 | Fixed | Other / General | (no match) | Low
11 | Engine Type List | UI | Should | None | Sort the engine type list in alphabetical sequence | 2026-03-17 | Ray | Refer to Screen Capture | Enhancement | 0 | 0 | Not a bug, to be addressed as new request | 0 | Low, fixed | 0 | Fixed | Other / General | (no match) | Low
16 | Input Type | UI | Should | None | Please update the default value to "Engine", currently is "Others". HAESL major business is "Engine". | 2026-03-17 | Ray | N/A | Enhancement | 0 | 0 | Changes to be done | 0 | Low, fixed | 0 | Fixed | Other / General | (no match) | Low
17 | System | System | Must | Bug | Unstable of system access, frequently time out/no response when access the system main page, active streamer page | 2026-03-17 | Ray | Refer to Screen Capture | Bug | P4 | 0 | Need more details from HAESL on timeout duration and to be verified against NFR | 0 | high, operational risk | 0 | Not yet fix | Other / General | (no match) | high
18 | System | System | Should | None | Please remove the "Overview" button if nothing was developed under this page | 2026-03-17 | Ray | Refer to Screen Capture | Enhancement | 0 | 0 | To be removed | 0 | Low, fixed | 0 | Fixed | Other / General | (no match) | Low
19 | Admin - Template Management | System | Must | Bug | When two users edit the same template and press save, system will create two templates with the same name. If we delete either one of them, both of the template will be deleted. Could the system lock the template if it is being edit to solve this problem? Co-edit issue | 2026-03-17 | Edmond | Refer to Screen Capture | Bug | P4 | 0 | Needs to be addressed | 0 | high, bug | 0 | Not yet fix | Other / General | (no match) | high
35 | Streamer - Induction update | System | Must | Bug | On the streamer page, the induction date shows 19 Mar, which does not match the edit page showing 12 Mar. | 2026-03-18 | Edmond | Refer to Screen Capture | Bug | P4 | 0 | Needs to be addressed | 0 | high, fixed | 0 | Fixed | Other / General | (no match) | high
36 | Planner - Create Streamer / Edit Streamer | System | Must | None | 1.If I press the selection box for module 31 and then press the selection box for module 32, the selection boxes for M31 & M32 will keep showing up 2. Selection box is too small, need to waste time to find the choice, if i click the selection box it can show all options, that will be better. | 2026-03-18 | Ming | Refer to Screen Capture | Enhancement | 0 | 0 | All modules to be shown as per screenshot, @Ray to confirm the change | 0 | medium, fixed | 0 | Fixed | Other / General | (no match) | medium
38 | Admin - Template Edit / | UI | Must | rework | Content and header is not aligned Duplicated, Refer to #7 | 2026-03-18 | Chris | 0 | Bug | P4 | 0 | Known issue, Raised with Syncfusion and is pending fix | 0 | Low, not yet fixed | 0 | Not yet fix | Other / General | (no match) | Low
39 | Planner - Menu Side Bar | UI | Must | Bug | The label by the hover effect on the menu button is blocked for the button navigation | 2026-03-18 | Chris | 0 | Bug | P4 | 0 | Move the hover text to the side | 0 | low, fixed | 0 | Fixed | Other / General | (no match) | low
44 | Planner -> Streamer -> Active Steamers | System | Must | Bug | 1. I entered the induction date as 03 Mar 2026; however, it is displaying as 23 Feb 2026. Please advise if incorrect data was entered. 2. The induction date cannot be amended to 03 Mar 2026. | 2026-03-19 | Ricky | Refer to Screen Capture | Bug | P3 | 0 |  | 0 | high. Fixed | 0 | Fixed | Other / General | (no match) | high. Fixed
45 | Planner -> Streamer -> Create Streamer | System | Must | Bug | Module Set → Sales Order: Unable to display multiple Sales Orders (S/Os). Please confirm whether “Trent 1000” is represented as “Trent 100 TEN” in the workscope. | 2026-03-19 | Ricky | Refer to Screen Capture | 0 | 0 | 0 |  | 0 | Removed | 0 | Closed | Other / General | (no match) | Removed
46 | Planner -> Streamer -> Create Streamer | System | Must | Bug | Why can duplicate Sales Orders (S/Os) be displayed? | 2026-03-19 | Ricky | Refer to Screen Capture | 0 | 0 | 0 | 0 | 0 | Removed | 0 | Closed | Other / General | (no match) | Removed
47 | Planner -> Streamer -> Create Streamer | System | Must | Bug | Issue: When creating Module M33 only, the system still displays other modules in the result/list view. Note: A valid template is in use; therefore, this issue is unlikely to be template‑related. | 2026-03-19 | Ricky | Refer to Screen Capture | 0 | 0 | 0 |  | 0 | Removed | 0 | Closed | Other / General | (no match) | Removed
48 | Active Streamer > Edit Streamer | System | Must | Bug | Module still in the streamer after remove it in the edit mode and save if the module already removed in the admin setting. | 2026-03-19 | Ray | N/A | Bug | P3 | 0 | Not clear, please provide steps and additional details @Ray | 0 | Removed | 0 | Closed | Other / General | (no match) | Removed
52 | Planner > Streamers | System | Should | Rework | the user just want to cancel one of the filter fields but only one button to "Clear All" | 2026-03-19 | Chris | 0 | Enhancement | 0 | 0 | Currently as per requirement, Please details if any modification required | 0 | low, performance issue | 0 | Not yet fix | Other / General | (no match) | low
53 | Edit Streamer | System | Must | Bug | Engine/Module Set multiple sales order for each module, when user edit the streamer all sales order in module become the same sales order | 2026-03-19 | Ray | Refer to Screen Capture | Bug | P3 | 0 | Fixed | 0 | high, fixed | 0 | Fixed | Other / General | (no match) | high
54 | Planner > Streamers | System | Must | Rework | Inconsistent positions on the TRT indication even it can be blocked by the icon | 2026-03-19 | Chris | 0 | Bug | P3 | 0 | To be fixed | 0 | low, display issue | 0 | Not yet fix | Other / General | (no match) | low
58 | Admin - Template Management | Gantt View | Should | Rework | Vertical Scroll Bar is visible all the time but not the horizontal one. Ensure the Horizontal Scroll Bar is visible all the time. | 2026-03-20 | Eugene | Refer to Screen Capture | Enhancement | 0 | 0 | To be done | 0 | medium, performance issue | 0 | Not yet fix | Other / General | (no match) | medium
60 | Admin - Template Management | Gantt View | Should | Rework | Put a space before and after hypen (-) | 2026-03-20 | Eugene | Refer to Screen Capture | Enhancement | 0 | 0 | To be done | 0 | medium, performance issue | 0 | Not yet fix | Other / General | (no match) | medium
66 | Test Plan | System | Must | Bug | Fail to upload test plan. When click the preview button, system error prompt | 2026-04-01 | Ray | Refer to Screen Capture | Bug | P3 | 0 | 0 | 0 | High, bug | 0 | Not yet fix | Other / General | (no match) | High
76 | Test Slot | System | Must | Bug | F01. Test Plan Upload fails intermittently | 2026-04-02 | Praveen on Ray's Behalf | 0 | Bug | P3 | 0 | We are looking into this and are trying to reproduce this, will be addressed in Patch 1 | 0 | High | 0 | 0 | Other / General | (no match) | High
84 | Streamers->create streamer | System | Should | 0 | No error message is shown when mandatory input data is missing. | 2026-04-06 | Edmond | Refer to Screen Capture | None | 0 | 0 | No error message will be shown but wont let the user proced further without filling the mandatory fields the uesr cannot proceed further | 0 | Removed | 0 | Closed | Other / General | (no match) | Removed
85 | Streamers->create streamer | System | Should | 0 | Can't type induction date. | 2026-04-06 | Edmond | Refer to Screen Capture | None | 0 | 0 | User needs select from Date picker as per design. Manual entry can cause format inconsistency and errors | 0 | Removed | 0 | Closed | Other / General | (no match) | Removed
86 | Streamers->create streamer | System | Should | 0 | if create error template (engine template /module template ) can't change to Module template from Engine Template Ray: there are no input type template classification in system, issue closed | 2026-04-06 | Edmond | Refer to Screen Capture | None | 0 | 0 | Need more details from HAESL @Ray | 0 | Removed | 0 | Closed | Other / General | (no match) | Removed
87 | Streamers->create streamer | System | Should | 0 | When creating a TRT, if “Engine” is selected as the input type, it should accept numbers only. There should be validation to check whether any incorrect (non‑numeric) input is entered. For system flexibity, this validation is not necessary at this moment, issue closed | 2026-04-06 | Edmond | Refer to Screen Capture | Bug | P4 | 0 | Engine validation required @Ray | 0 | Removed | 0 | Closed | Other / General | (no match) | Removed
88 | Streamers->create streamer | System | Should | 0 | 1.It is not possible to change only the streamer name. 2. after update streamer name .the streamer name didn't change. Ray: template name is generate by a default format and not suppose for edit, issue closed | 2026-04-06 | Edmond | Refer to Screen Capture | Enhancement | 0 | 0 | Streamer name change is what type @Ray | 0 | Removed | 0 | Closed | Other / General | (no match) | Removed
91 | Streamers->create streamer | System | Should | 0 | can't delete error template TBD | 2026-04-06 | Edmond | Refer to Screen Capture | None | 0 | 0 | Screenshot missing, needs additional details @Ray | 0 | Removed | 0 | Closed | Other / General | (no match) | Removed
93 | Planner - Create Streamer | UI | 0 | UI | There is an issue with the date display order. TBD | 2026-04-06 | Edmond | Refer to Screen Capture | None | 0 | 0 | As per requirements, user can click on the Test Date filter and sort accordingly | 0 | Removed | 0 | Closed | Other / General | (no match) | Removed
95 | Planner -> Engine Update | System | 0 | 0 | How to Use the "Offset Module" Function | 2026-04-06 | Ricky | 0 | None | 0 | 0 | 0 | 0 | Removed | 0 | Closed | Other / General | (no match) | Removed
110 | User Setting | System | Must | Bug | Unable to search the user from the access right list after add the user, and the user unable to access the streamer too. | 2026-04-10 | Ray | Refer to Screen Capture | Bug | P1 | 0 | Being worked on | 0 | High, bug | 0 | 0 | Other / General | (no match) | High
123 | Streamer > Export | System | Should | Enhancement | No matter for PDF or CSV file, to enhance information exported for below columns included: ¦ Streamer Name ¦ ESN ¦ Sales Order ¦ Visit Type ¦ Customer Code ¦ Input Type ¦ Induction Date ¦ Test Date ¦ Status (WIP/Completed/Disabled) ¦ | 2026-04-15 | Chris | 0 | 0 | 0 | 0 |  | 0 | Low, but performance issue | 0 | 0 | Other / General | (no match) | Low
128 | Streamer > Streamer Edit Page | System | Must | Bug | it cannot be refreshed by "Refresh (Ctrl + R)" | 2026-04-15 | Chris | 0 | 0 | 0 | 0 | 0 | 0 | Low, bug | 0 | 0 | Other / General | (no match) | Low
130 | Test Slot Preview | System | Must | Bug | The remark is not correct. For example the engine is in test plan but the remark's comment said the engine is not in the test plan. | 2026-04-15 | Eugene | 0 | 0 | 0 | 0 | 0 | 0 | High, bug | 0 | 0 | Other / General | (no match) | High
141 | Active Streamer | System | Must | Rework | Not Able to search the streamer by module S/N | 2026-04-17 | CR | N/A | 0 | 0 | 0 | 0 | 0 | Medium | 0 | 0 | Other / General | (no match) | Medium
144 | Active Streamer | System | Must | Bug | Unable to select or view previous issue of streamer | 2026-04-17 | Ray | N/A | 0 | 0 | 0 | 0 | 0 | Medium | 0 | 0 | Other / General | (no match) | Medium
145 | Planner -> Streamer | System | 0 | Rework | HAESL Visit Type: no RTP | 2026-04-18 | Ricky | 0 | 0 | 0 | 0 | 0 | 0 | Medium | 0 | 0 | Other / General | (no match) | Medium
6 | Planner - Create Streamer | System | Must | Bug | Dispatch Module S/N cannot be updated. | 2026-03-16 | Ricky | Refer to Screen Capture | None | 0 | 0 | As per requirement | 0 | Medium | 0 | Fixed | Swap Module | dispatch module | Medium
56 | Planner > Streamers | System | Should | Rework | The top‑level task has been completed; please proceed to complete the sub‑tasks. Engine Level Task update PCD, all module level task will update too (not included the swap module task) | 2026-03-19 | Ricky | Refer to Screen Capture | 0 | 0 | 0 | 0 | 0 | High | 0 | Not yet fix | Swap Module | swap | High
61 | Planner -> Streamer -> Create Streamer | System | Must | Bug | The dispatched Module S/N cannot be changed at the first input. Resolved: Click swap module button and click the Set as Default | 2026-03-24 | Ricky | Refer to Screen Capture | None | 0 | 0 | Not clear understanding, please provide details @Ricky | 0 | Removed | 0 | Closed | Swap Module | swap | Removed
81 | Module Swap | System | Must | Bug | F09 - . Module swap assistance FAIL, same module cannot swap to more than one engine streamer at the same time. Module could swap from Engine A then Engine B, but not Engine A and Engine B. | 2026-04-02 | Praveen on Ray's Behalf | 0 | Bug | P3 | 0 | Fixed after we received feedback during Demo 3. Will be available in Patch 1 | 0 | High | 0 | 0 | Swap Module | swap | High
92 | Planner - Create Streamer | System | Must | Bug | 1. The “Dispatch Module S/N” cannot be changed (again). 2. Please add a Back function next to Save. 3. Please sort the “Module ATA”. | 2026-04-06 | Ricky | Refer to Screen Capture | None | 0 | 0 | 1. Dispatch module is not editable as text. It should be selected from off-module list 2. As per design 3. In Create Streamer page, it is sorted as per Module ATA and it needs to be sorted in Preview screen | 0 | Low | 0 | 0 | Swap Module | off-module | Low
109 | Create Streamer | System | Must | None | All "Dispatch Module S/N" set to RETAIN, remove the "Set to Default" button in swap module pop up page | 2026-04-09 | Ray | N/A | None | 0 | 0 | 0 | 0 | Medium, design fault | 0 | 0 | Swap Module | swap | Medium
126 | Off-module list > Export | System | Should | Enhancement | To align with other export function, please add the export to PDF & CSV with the columns included: ¦ Module Name ¦ Module Status ¦ Module ATA ¦ Module SN ¦ Work Level ¦ Engine Type ¦ Cust. Code ¦ Sales Order ¦ Induction Date ¦ Module Build Date ¦ To ESN ¦ Ex ESN ¦ Return to Cust ¦ Reduce to Parts ¦ | 2026-04-15 | Chris | 0 | 0 | 0 | 0 |  | 0 | Low, but performance issue | 0 | 0 | Swap Module | off-module | Low
1 | Admin - Task Owner Setting | System | Must | Bug | Duplicate User show in the list when click "MR" | 2026-03-16 | Ray | Refer to Screen Capture | Bug | P4 | 0 | Suspecting this can be observed when two users performing same operation at atime. Not able to reproduce it in dev by single user | 0 | Low, no issue now | 0 | Fixed | Task Owner Action | task owner | Low
7 | Planner - Task | UI | Should | Bug | The table cells borders is not align | 2026-03-17 | Ray | Refer to Screen Capture | Bug | P4 | 0 | Working with Syncfusion on it | 0 | Low, not yet fixed | 0 | Not yet fix | Task Owner Action | task | Low
8 | Planner - Task | System | Must | Bug | Showing unexpected date range after filter | 2026-03-17 | Ray | Refer to Screen Capture | None | 0 | 0 | 0 | 0 | High, function disappeared | 0 | Not yet fix | Task Owner Action | task | High
9 | Planner - Task | System | Must | Rework | Missing implement of Post UAT item U08 | 2026-03-17 | Ray | Refer to Screen Capture | None | 0 | 0 | 0 | 0 | Removed | 0 | Closed | Task Owner Action | task | Removed
12 | Admin - Template Create - Task Selection | System | Must | None | For Module Level tasks (Items 5, 9, 15, 32, 33, and 39), updating the top‑level item should also update the sub‑tasks automatically. | 2026-03-17 | Edmond | Refer to Screen Capture | None | 0 | 0 | No action | 0 | High, operational risk | 0 | Fixed | Task Owner Action | task | High
21 | Planner - Create Streamer | System | Must | Bug | When create streamer, module level task was unexpected disabled. | 2026-03-17 | Ray | Refer to Screen Capture | Bug | P4 | 0 | Need additional information | 0 | Closed | 0 | Closed | Task Owner Action | task | Closed
22 | Admin - Gate Setting, Module Setting & Task Setting | System | Must | Bug | The gate setting or module setting change, the template won't have any update. e.g. I delete the Gate 1B, but the Gate 1B still in the template. All the setting should be synchronize. | 2026-03-17 | Ray | Refer to Screen Capture | None | 0 | 0 | As per requirement | 0 | High | 0 | Fixed | Task Owner Action | task | High
23 | Tasks | System | Must | Bug | Unexpected error after input ACD for the task and press save. | 2026-03-17 | Ray | Refer to Screen Capture | Bug | P4 | 0 | Unable to produce bug, Additional information needed | 0 | high, fixed | 0 | Fixed | Task Owner Action | ACD | high
26 | Tasks | System | Must | Bug | After enter a late PCD, the reason for delay list is nothing inside | 2026-03-17 | Ray | Refer to Screen Capture | Bug | P3 | 0 | Fixed | 0 | High, bug | 0 | Fixed | Task Owner Action | PCD | High
27 | Tasks - Task Owner Filter | System | Must | Bug | The Task Owner drop-down list is not syncing with the latest Task Owner settings in Admin. Please update the list items and sort them in alphabetical order. | 2026-03-18 | Ray | Refer to Screen Capture | Bug | P4 | 0 | Needs to be synced | 0 | Medium, bug | 0 | Fixed | Task Owner Action | task owner | Medium
28 | Streamer - Module Level Task | System | Should | None | The sequence of module level task should follow the module sequence in admin setting | 2026-03-18 | Ray | Refer to Screen Capture | Enhancement | 0 | 0 | To be changed as mentioned | 0 | Medium, performance issues | 0 | Fixed | Task Owner Action | task | Medium
29 | Tasks - Task Owner Filter | System | Must | Bug | Duplicate selection items found. | 2026-03-18 | Ray | Refer to Screen Capture | Bug | P4 | 0 | Needs to be addressed | 0 | medium, fixed | 0 | Fixed | Task Owner Action | task owner | medium
30 | Tasks | System | Must | Bug | Planner / Task Owner should not able to disable a task when the task already completed. (L02) | 2026-03-18 | Ray | Refer to Screen Capture | None | 0 | 0 | Changes as per L02 | 0 | medium, fixed | 0 | Fixed | Task Owner Action | task owner | medium
32 | Admin - Task Selection update | System | Must | Bug | When user update column Start Day and Duration value, system will auto selected the row, it is not what we expect. | 2026-03-18 | Ricky | Refer to Screen Capture | Bug | P4 | 0 | As per email with Ray, auto selection to be removed | 0 | medium, operational risk | 0 | Fixed | Task Owner Action | task | medium
33 | Admin - Task Selection update | System | Must | Bug | When user update module level task Start Day and Duration value and save, the value remain the past value in the edit page, but with the update value in the preview page. | 2026-03-18 | Ricky | Refer to Screen Capture | Bug | P4 | 0 | As per email with Ray, Save should reflect change in the same page | 0 | medium, bug | 0 | Fixed | Task Owner Action | task | medium
34 | Admin - Task Selection update | System | Must | None |  | 2026-03-18 | Ricky | N/A | Bug | P4 | 0 | Working as per requirement, module level tasks to be updated manually | 0 | Removed | 0 | Closed | Task Owner Action | task | Removed
37 | Admin - Template Edit | UI | Must | rework | Header of Task Selection (Step 2) is hidden and the header text NOT be fit into width of columns | 2026-03-18 | Chris | 0 | Bug | P4 | 0 | Needs more details | 0 | medium, performance issue | 0 | Not yet fix | Task Owner Action | task | medium
40 | Planner - Tasks | UI | Must | Bug | The horizontal scroll-bar is hidden on the bottom | 2026-03-18 | Chris | 0 | Bug | P4 | 0 | Always show scroll bar | 0 | medium, operational risk | 0 | Not yet fix | Task Owner Action | tasks | medium
41 | Admin - Template Edit / | System | Must | Bug | All the fields setting in template should not change even any change happened in the task management. But now when the user go to the edit streamer page, latest task setting will auto update the setting in template edit page. | 2026-03-18 | Edmond | Refer to Screen Capture | None | 0 | 0 | As per requirement, BRD 4.2.9 9. Any changes(updating and deleting) in the Tasks management will NOT affect in Templates | 0 | High | 0 | Fixed | Task Owner Action | task | High
43 | Planner -> Streamer -> Active Steamers | System | Must | Bug | The Actual Completion Date was completed on 07 Mar 2026, but it is not reflected in the system.(Fxied) Task disable/enable without any confirmation (User need to click save to make changes) | 2026-03-19 | Ricky | Refer to Screen Capture | Bug | P3 | 0 |  | 0 | medium, operational risk | 0 | Not yet fix | Task Owner Action | actual completion | medium
49 | Template Management - Edit Template | System | Must | Bug | the template edit page allow double click the fields(Task owner, Start Day, Duration) to access the target fields to do modification, but it is not working. The modification only happen the user update the fields by click the "Edit" Pencil button | 2026-03-19 | Ray | N/A | Bug | P4 | 0 | 0 | 0 | Medium | 0 | Fixed | Task Owner Action | task owner | Medium
50 | Planner -> Streamer -> Amend Streamer | System | Should | Rework | When existing engine streamer module work level change and load a new template or not, all the existing tasks data should be keep. | 2026-03-19 | Ricky | Refer to Screen Capture | None | 0 | 0 | Not clear, need understanding @Ray | 0 | high, operational risk | 0 | Not yet fix | Task Owner Action | tasks | high
51 | Planner > Tasks Edit | System | Must | Bug | Once I input non-date on the Acutal Completion Date, PCD is changed unexpected. Please validate if the ACD input is a number | 2026-03-19 | Chris | 0 | Bug | P4 | 0 | To be checked | 0 | high, fixed | 0 | Fixed | Task Owner Action | PCD | high
55 | Planner > Streamers | System | Must | Bug | All tasks have the Actual Completion Date entered as 19 Mar 2026, but the system displays 18 Mar 2026. | 2026-03-19 | Ricky | Refer item 56 to Screen Capture | None | 0 | 0 | Please provide Streamer details. @Ray, @Ricky | 0 | High | 0 | Fixed | Task Owner Action | actual completion | High
57 | Planner > Streamers | System | Must | Bug | For Engine 26121: Task 6 – Components Receipt at Vendor The task Finish Date is 25 Mar 2026; however, the Actual Completion Date was updated to 18 Mar 2026 due to early completion. Task 7 – Parent Task (Components Sentencing) The Finish Date remains 01 Apr 2026 and was not automatically revised to 25 Mar 2026, despite Task 6 being completed earlier. | 2026-03-19 | Ricky | Refer to Screen Capture | 0 | 0 | 0 |  | 0 | Removed | 0 | Closed | Task Owner Action | actual completion | Removed
59 | Admin - Template Management | Gantt View | Should | Rework | The Arrow Line and the Wording of Task Description should not be overlapped | 2026-03-20 | Eugene | Refer to Screen Capture | Bug | 0 | 0 | To be done | 0 | medium, performance issue | 0 | Not yet fix | Task Owner Action | task | medium
65 | Task Update | System | Must | Bug | Parent Child Relationship do not cover all current practises 1. WHEN Parent PCD + 2 days, THEN Child PCD + 2 days - Success 2. WHEN Parent PCD - 2 days, THEN Child PCD - 2 days - Failure 3. WHEN Parent ACD + 2 days, THEN Child PCD + 2 days - Failure 4. WHEN Parent ACD - 2 days, THEN Child PCD - 2 days - Failure | 2026-03-27 | Eugene | N/A | Bug | P4 | 0 | To be verified | 0 | High, bug | 0 | Not yet fix | Task Owner Action | PCD | High
67 | Task Update | System | Must | Bug | Text in the "Comments" disappeared after save | 2026-04-01 | Ray | Refer to Screen Capture | Bug | P4 | 0 | 0 | 0 | High, bug | 0 | Not yet fix | Task Owner Action | task | High
71 | Task Update | System | Must | Bug | L02 - Task Enable/Disabled : User needs to click on save button | 2026-04-02 | Praveen on Ray's Behalf | 0 | Bug | P4 | 0 | Enable/Disable to make the change and click on save. To be fixed in Patch 2 | 0 | Low | 0 | 0 | Task Owner Action | task | Low
73 | Task Screen | System | Must | Bug | U04 - Interface issue - Window not moveable | 2026-04-02 | Praveen on Ray's Behalf | 0 | Bug | P4 | 0 | To be fixed in Patch 2 | 0 | Medium | 0 | 0 | Task Owner Action | task | Medium
75 | Task Screen | System | Must | Bug | U12 - Task Screen : Hard to identify streamer and task | 2026-04-02 | Praveen on Ray's Behalf | 0 | Bug | P4 | 0 | Syncfusion doesn’t support 2 columns. Font size of the Streamer name to be increased with Streamer name in bold | 0 | Medium | 0 | 0 | Task Owner Action | task | Medium
77 | Task Screen | System | Must | Bug | U12 - Task Screen : Hard to identify streamer and task Duplicated, refer to #75 | 2026-04-02 | Praveen on Ray's Behalf | 0 | Bug | P4 | 0 |  | 0 | Removed | 0 | Closed | Task Owner Action | task | Removed
78 | Task Screen | System | Must | Bug | F03 - all the input in the comments box disappeared after save | 2026-04-02 | Praveen on Ray's Behalf | 0 | None | 0 | 0 | Not a bug, works as expected | 0 | High | 0 | 0 | Task Owner Action | task | High
82 | Admin -> Template Management -> Amendment | System | Must | Bug | The Task Owner update cannot be changed to another section code. For example, after clicking “Save” and returning to review, no change is reflected. | 2026-03-04 | Ricky | Refer to Screen Capture | Bug | P3 | 0 | Changes reflects in review screen but if the user goes back to the screen then the changes not reflected, Issue fixed and pending deployment | 0 | Medium | 0 | Fixed | Task Owner Action | task owner | Medium
83 | Admin -> Template Management | System | Must | Bug | Tasks 11, 16, 21, and 25 are hidden and can't add back | 2026-04-03 | Ricky | Refer to Screen Capture | Bug | P1 | 0 | Bug. fixed | 0 | High | 0 | Fixed | Task Owner Action | tasks | High
89 | Streamers-> Task | System | Should | 0 | 1.In the Task section, only tasks that have not yet been entered should be displayed. 2.after update actual date and save .tarage Engine should not close | 2026-04-06 | Edmond | Refer to Screen Capture | None | 0 | 0 | Not clear @Ray | 0 | Medium | 0 | Not yet fix | Task Owner Action | task | Medium
90 | Streamers-> Task | System | Should | 0 | no print function in task section TBD | 2026-04-06 | Edmond | Refer to Screen Capture | None | 0 | 0 | Not a requirement | 0 | Removed | 0 | Closed | Task Owner Action | task | Removed
94 | Planner - Create Streamer | System | Should | Bug | Task Selection → Task Owner (Create & Review pages): The data shown does not match. | 2026-04-06 | Ricky | Refer to Screen Capture | Bug | P4 | 0 | Template Create and review is not the same after changes | 0 | High, bug | 0 | 0 | Task Owner Action | task owner | High
96 | Planner - Task | System | Must | 0 | 1. Please add a checkbox to select Not Complete tasks. 2. Do not hide the task. 3. How can the Not Complete tasks be printed out? | 2026-04-06 | Ricky | Refer to Screen Capture | Enhancement | 0 | 0 | 1. Task Status can be added as filter in the Task screen @Ray - need your acceptance 2. Need additional details 3. Print option in task screen not part of requirement | 0 | Medium | 0 | 0 | Task Owner Action | task | Medium
97 | Planner - Create and Amend | System | Must | 0 | Task 10 & Task 15 – Task Owner Logic Module Level Task Owner If Module is L3 or L4, then Task Owner = Bench If Module Is L1 or L2, then Task Owner = Module Repair (except for Module 34 which the task owner always be Module Change regardlesss of L1, L2, L3 or L4) Engine Level Task Owner If any of the Module Level task owner is Bench, then the Engine Level task owner is Bench If the Active Module task owner consist both Module Repair or Module Chnage (for Module 34), then the Engine Level task owner is Module Repair If the Active Module task owner consist only Module Repair, then the Engine Level task owner is Module Repair If the only Active Module task owner is Module Change (for Module 34), then the Engine Level task owner is Module Change (If only M34 active, Task 10 not active) If none of the Module is active, then the Engine Level is also not active Note. Module is not active when work level is L1, New, S/Rec'd Applicable Modules M31, M32, M33, M34, M41, M51, M52, M61, Engine Mount New or S/R Status Blank or MR | 2026-04-06 | Ricky | 0 | Enhancement | 0 | 0 | Not covered in the requirement | 0 | High, operational risk | 0 | 0 | Task Owner Action | task owner | High
98 | Planner - Task | System | Must | 0 | Table line not match Duplicated, Refer to #7 | 2026-04-07 | Edmond | Refer to Screen Capture | Bug | P4 | 0 | Syncfusion issue, working with them | 0 | low, not yet fixed | 0 | 0 | Task Owner Action | task | low
99 | Tasks | System | Must | Enhancement | Add task status filter in the page, planner/task owner could select WIP/Disabled/Completed to filter the task list | 2026-04-08 | Ray | N/A | Enhancement | 0 | 0 | 0 | 0 | Medium, operational risk | 0 | 0 | Task Owner Action | task owner | Medium
100 | Tasks | System | Must | 0 | Add toggle button to expand the task list for each streamer | 2026-04-08 | Ray | N/A | Enhancement | 0 | 0 | Toggle button attribute @Ray | 0 | Low | 0 | 0 | Task Owner Action | task | Low
101 | User access | System | Must | None | Staff/Task Owner only able to view Streamer and Tasks | 2026-04-09 | Ray | N/A | Enhancement | 0 | 0 | As per requirement | 0 | low, fixed | 0 | 0 | Task Owner Action | task owner | low
102 | Tasks | System | Must | Enhancement | Add Task Name and Sales Order no. on task editing page | 2026-04-09 | CCB | N/A | Enhancement | 0 | 0 | 0 | 0 | Medium, operational risk | 0 | 0 | Task Owner Action | task | Medium
104 | Tasks | System | Must | Enhancement | Add Task Status filter in Task view page to fiter WIP/Disabled/Completed task status | 2026-04-09 | Logistics | N/A | Enhancement | 0 | 0 | Duplicate 99 | 0 | Medium, operational risk | 0 | 0 | Task Owner Action | task | Medium
105 | Tasks | System | Must | Enhancement | Monthly filter is not user friendly to view all task belong to me. Could the duration become unlimited to show all date? | 2026-04-09 | Logistics | N/A | Enhancement | 0 | 0 | Provide exact requirement, Do you want a see Quarter or Yearly view? With all duration, the tasks will be not be visible @Ray | 0 | Medium, performance issue | 0 | 0 | Task Owner Action | task | Medium
106 | Admin - Task Management | System | Must | Bug | For the XWB97 HSV Template, a mismatch has again been identified between the amendment pages and the displayed data for Tasks 15, 32, and 33. | 2026-04-09 | 0 | Refer to Screen Capture | Bug | 0 | 0 |  | 0 | High, operational risk | 0 | 0 | Task Owner Action | task | High
107 | Tasks | System | Must | Enhancement | Task Owner should not able to input futher date within a date range | 2026-04-09 | CCB | 0 | Enhancement | 0 | 0 | Please provide exact requirement @Ray | 0 | Medium, operational risk | 0 | 0 | Task Owner Action | task owner | Medium
112 | Tasks | System | Must | None | Actual Completion Date Should not allow user to select future date. User only able to select today or back date. | 2026-04-13 | Ray | N/A | Enhancement | 0 | 0 | 0 | 0 | Medium, operational risk | 0 | 0 | Task Owner Action | actual completion | Medium
115 | Task | System | Must | None | Only Planner could disable task (TBC) | 2026-04-14 | Ray | N/A | 0 | 0 | 0 | 0 | 0 | Medium, operational risk | 0 | 0 | Task Owner Action | task | Medium
117 | Template - task selection | System | Must | Rework | In task selection page, the header row should be frozen | 2026-04-14 | Ray | Refer to Screen Capture | 0 | 0 | 0 | 0 | 0 | Low, bug | 0 | 0 | Task Owner Action | task | Low
118 | Template - task selection | System | Must | Bug | When I edit a task details (e.g. task owner), after I confirm the screen will focus to other area. | 2026-04-14 | Ray | N/A | 0 | 0 | 0 | 0 | 0 | Medium, the position of the form should be sticky after action triggered | 0 | 0 | Task Owner Action | task owner | Medium
119 | Task | System | Must | Bug | After actual completion date updated, no log display for the change | 2026-04-14 | CR | N/A | 0 | 0 | 0 | 0 | 0 | Medium, bug | 0 | 0 | Task Owner Action | actual completion | Medium
122 | streamer -> task | System | Must | Rework | task action log unclear.the comments commented by last user should stay in comments box. | 2026-04-14 | Ray | N/A | 0 | 0 | 0 | 0 | 0 | Medium | 0 | 0 | Task Owner Action | task | Medium
124 | Streamer > Edit Streamer > Export | System | Should | Enhancement | No matter for PDF or CSV file, to enhance information exported for below columns included: ¦ Task No ¦ Task Name ¦ Task Owner ¦ Duration ¦ Start Date ¦ Finish Date ¦ Projected Completion Date ¦ Actual Completion Date ¦ | 2026-04-15 | Chris | 0 | 0 | 0 | 0 |  | 0 | Low, but performance issue | 0 | 0 | Task Owner Action | task owner | Low
125 | Tasks Page > Export | System | Should | Enhancement | To align with Export function with Streamer page, to add Export to PDF & CSV and generate the columns included: ¦ Task Owner ¦ Task ID ¦ Duration ¦ Start Date ¦ Finish Date ¦ Projected Completion Date ¦ Actual Completion Date ¦ Induction Date ¦ Test Date ¦ Reason of Delay ¦ Comments ¦ Task status (WIP/Completed/Disabled) ¦ | 2026-04-15 | Chris | 0 | 0 | 0 | 0 |  | 0 | Low, but performance issue | 0 | 0 | Task Owner Action | task owner | Low
127 | Test Slot | System | Must | Bug | 21954 Test Plan Excel File showes 05/Jun. After test plan file upload, the Project Completion Date of Task 39 - Test (MST) still unchanged on 11/May | 2026-04-15 | Eugene | 0 | 0 | 0 | 0 | 0 | 0 | High, critical bug | 0 | 0 | Task Owner Action | task | High
129 | Test-slot > Upload | System | Must | Enhancement | For Task Owner & Staff, the function called "Upload" should be not provided. | 2026-04-15 | Chris | 0 | 0 | 0 | 0 | 0 | 0 | Medium, operational risk | 0 | 0 | Task Owner Action | task owner | Medium
134 | Tasks | System | Must | Rework | Task action log not really record all the changes, e.g. not record the delay reason, not record the PCD date changes | 2026-04-17 | Various | Refer to screen capture | 0 | 0 | 0 | 0 | 0 | Low | 0 | 0 | Task Owner Action | PCD | Low
136 | Tasks | System | Should | Rework | Add "Other Reason" in the delay reason dropdown list | 2026-04-17 | CCB | N/A | 0 | 0 | 0 | 0 | 0 | Low | 0 | 0 | Task Owner Action | delay | Low
138 | Tasks | System | Must | Rework | As a task owner, currently design is not user-friendly, I can not focus on any WIP tasks belong to my department. Suggest to add below filters: Task PCD in Today/This Week/Overdue | 2026-04-17 | Various | N/A | 0 | 0 | 0 |  | 0 | Medium | 0 | 0 | Task Owner Action | task owner | Medium
140 | Tasks | System | Must | Rework | As a task owner, I also need to know the below infomation in the task pop up ESN, Module S/N(if it is a module level task), Task Name, Sales Order, Task Owner, Streamer Status. Add an area to shows all streamer tasks status. | 2026-04-17 | Various | N/A | 0 | 0 | 0 |  | 0 | Low | 0 | 0 | Task Owner Action | task owner | Low
143 | Active Streamer | System | Must | Rework | In the streamer page to view all the tasks for streamer, column name "Actual Finish Date" should be "Actual Completion Date" | 2026-04-17 | Ray | Refer to screen capture | 0 | 0 | 0 | 0 | 0 | Low | 0 | 0 | Task Owner Action | actual completion | Low
146 | Planner -> Streamer | System | 0 | Rework | Task 9, (10), 15, 32, 33 – Task Owner Logic If Tasks 9, (10), 15, 32, and 33 are all at Level 1 (L1) and disabled at the module level, please also disable the engine level. If a module is upgraded from Level 1 (L1) to Level 2 (L2), the corresponding applicable items shall be enabled. | 2026-04-18 | Ricky | 0 | 0 | 0 | 0 |  | 0 | High, engine task is not aligned with module | 0 | 0 | Task Owner Action | task owner | High
147 | Planner -> Streamer | System | Must | Bug | Module SN change only – task data (Finish Date, PCD, ACD) to remain unchanged. Duplicted, refer to #50 | 2026-04-18 | Ricky | 0 | 0 | 0 | 0 |  | 0 | High, operational risk | 0 | 0 | Task Owner Action | PCD | High
62 | Admin - Template Management | Gantt View | Should | Rework | Since this is the template's grantt view, the display's start date and end date should be showing number instead of calendar date | 2026-03-24 | Eugene | Refer to Screen Capture | Bug | 0 | 0 | To be corrected | 0 | Low | 0 | Fixed | Task Owner View | calendar | Low
63 | Planner -> Streamer -> | System | Must | Bug | Tasks may be completed earlier than anticipated. Attempted to select today's date (25/03/2026), Project Completion Date cell does not allow for dates earlier than 03/04/2026. Why cannot earlier. Ray: The date selection in calendar in both PCD and ACD is not consistent, sometimes could input today -7, sometimes could input today -14. | 2026-03-24 | Ricky | Refer to Screen Capture | Bug | 0 | 0 | To be fixed | 0 | High | 0 | Not yet fix | Task Owner View | calendar | High
74 | Task Screen | System | Must | Bug | U09 - Custom Date Range filter | 2026-04-02 | Praveen on Ray's Behalf | 0 | Bug | P3 | 0 | Syncfusion currently doesnt support it, raised a ticket for resolution. Only Month view available as per calendar | 0 | Medium | 0 | 0 | Task Owner View | calendar | Medium
108 | Tasks | System | Must | Enhancement | My Tasks display format not user friendly. Cannot only focus with the outstanding issues. With Searching result : SP, Task 35, 84K, but still showing full Calendar date with no outstanding Task 35. And should not need to click each engine for checking if any outstanding. | 2026-04-09 | SP | 0 | Enhancement | 0 | 0 | Please provide the expected enhancement requirement @Ray | 0 | Medium, operational risk | 0 | 0 | Task Owner View | calendar | Medium
133 | Task Owner - Tasks | System | Must | Bug | The tasks view always have unexpected movement of the user view. When I click on a task at the bottom, after I save the task to view the changes, the screen will move back to the top of the calendar, not orginally I focus on. | 2026-04-17 | Ray | To be demo | 0 | 0 | 0 | 0 | 0 | Medium, the position of the form should be sticky after action triggered | 0 | 0 | Task Owner View | calendar | Medium